## Calendar 3.0
Participants
| Line # | Status | Sprint | Workstream | Focus Area | Key Topics | Original Date | Time | Revised Date (if applicable) | Duration (Hours) | DOC BAS PMO | Decision Making Forum | CS Participants
| 1 | Complete | 1 | PTR | SLA Posting Model Review | • Review SLA Posting Model • Standard USSGL postings for accounting events across EBS modules • Treasury Codes, USSGL Account DR/CR pairs validation | N/A | N/A |  | 1 | X
| 2 | Complete | 1 | PTR | PTR Requirements | Review any open requirements | N/A | N/A |  |  | X | X
| 3 | Complete | 1 | PTR | Ledger Overview | • Overview of the single consolidated DOC Ledger approach • Data Access Control functionality • Operating Units | 2020-10-13 | 1 PM - 3 PM |  | 2 | X | X
| 4 | Complete | 1 | SF Real Property | Disposals (RP) | Current As-Is Business Process Review Final Event Types - Disposal Type Final Event User Defined Fields | 2020-10-20 | 1 PM - 3 PM |  | 2 | X | X
| 5 | Pending | 1 | PRISM | Advanced Acquisition Planning Workshop | • Determine the following information: - Word templates - Folder structures - Document categories | 2020-10-21 | 9 AM - 5 PM |  | 8 | X | X
| 6 | Complete | 1 | SF Real Property | Reporting / Interfaces (RP) | Current As-Is Business Process Review Final Event Types - Disposal Type Final Event User Defined Fields | 2020-10-21 | 1 PM - 3 PM |  | 2 | X | X
| 7 | Pending | 1 | PTR | Plan to Report – BAS ACS Detailed Review | • CBS ACCS to BAS ACS Crosswalk • Sample Segment values • Transaction Accounting String • Program Code to Program Activity mapping | 2020-10-22 | 1 PM - 2 PM |  | 1 | X | X
| 8 | Complete | 1 | SF Real Property | Acquisition (RP) | Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) | 2020-10-22 | 10:00 AM - 11:30 AM |  | 1.5 | X | X | X
| 9 |  | 2 | PTR | Journal Approval Workflow | • Journal Approval Process Walkthrough • Approver Hierarchy • Email Notifications to preparer/approver | 2021-03-02 | 1 PM - 2 PM |  | 1 | X | X | X
| 10 |  | 2 | PTR | Journal Reversal (Manual) | • Auto Reversal • Manual-Entry Journal Reversal • Single - Entry Reversal business scenarios | 2021-03-04 | 1 PM - 2 PM |  | 1 | X | X | X
| 11 |  | 3 | PTR | G Invoicing Approach | • G Invoicing Integration approach • Understand known / current G Invoicing plan for PRISM & Oracle | 2021-02-23 | 1 PM - 2 PM |  | 1 | X | X
| 12 |  | 3 | PTR | G Invoicing Approach | • G Invoicing Integration approach • Understand known / current G Invoicing plan for PRISM & Oracle | 2021-03-09 | 1 PM - 3 PM |  | 2 | X | X | X
| 13 |  | 2 | PTR | Budget Entry/Funds Status Report | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report | 2021-01-14 | 1 PM - 3 PM |  | 2 | X | X
| 14 |  | 2 | PTR | Budget Entry/Funds Status Report | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report | 2021-03-25 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 15 |  | 3 | PTR | GTAS/DATA Act Reporting | • GTAS Attributes • DATA Act Configurations • Reporting guidance across Department; bureau submission | 2021-04-15 | 1 PM - 3 PM |  | 2 | X | X
| 16 |  | 3 | PTR | GTAS/DATA Act Reporting | • GTAS Attributes • DATA Act Configurations • Generating GTAS/DATA Act Reports | 2021-06-08 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 17 |  | 3 | PTR | Month End Close Process | • Month End Closing Definitions • Standard Year End Close Process | 2021-04-20 | 1 PM - 3 PM |  | 2 | X | X
| 18 |  | 3 | PTR | Month End Close Process | • Month End Closing Definitions • Standard Year End Close Process | 2021-06-10 | 1 PM - 3 PM |  | 2 | X | X | X
| 19 |  | 3 | PTR | Year End Close Process | • Year End Closing Definitions • Standard Year End Close Process | 2021-04-22 | 1 PM - 3 PM |  | 2 | X | X
| 20 |  | 3 | PTR | Year End Close Process | • Year End Closing Definitions • Standard Year End Close Process | 2021-06-15 | 1 PM - 3 PM |  | 2 | X | X | X
| 21 |  | 1 | PRISM | PRISM Requirements | Review any open requirements | N/A | N/A |  |  | X | X
| 22 | Complete | 1 | PRISM | Advanced Acquisition Planning Demo | • Building collaborative acquisition workspaces based on pre-defined templates • Adding, revising, and searching internal notes • Establishing and managing integrated project teams • Tracking acquisition-related data • Developing vendor deliverable schedules • Establishing acquisition milestone schedules • Developing acquisition packages using Microsoft Word and PDF templates • Generating an electronic contract file folder structure • Budget planning for year-over-year commitments and obligations | 2020-10-08 | 9 AM - 11 AM |  | 2 | X | X
| 23 | Complete | 1 | PRISM | Advanced Acquisition Planning Workshop | • Determine the following information: - Templates based on acquisition type - Note types - Data elements to capture - Integrated procurement teams | 2020-10-13 | 1 PM - 5 PM |  | 4 | X | X
| 24 | Complete | 1 | PRISM | Advanced Acquisition Planning Workshop | • Determine the following information: - Vendor deliverable schedules - Cost tracking and objective tabs - Milestones | 2020-10-15 | 9 AM - 5 PM |  | 8 | X | X
| 25 | Pending | 1 | OTC | Direct Invoicing / Invoice Interface | • Invoice Creation (Manual /invoice interface) • External systems interfacing to AR directly • Customer Holds • Confirm reporting requirements from COTS | 2020-10-26 | 1 PM - 3 PM |  | 2 | X | X
| 26 | Pending | 1 | PTR | PTR BAS ACS Detailed Review | • CBS ACCS to BAS ACS Crosswalk • Sample Segment values • Transaction Accounting String • Program Code to Program Activity mapping | 2020-10-27 | 1 PM - 3 PM |  | 2 | X | X | X
| 27 | Cancelled | 1 | SF Real Property | Utilization (RP) | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | 2020-10-27 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 28 | Cancelled | 1 | Projects | Cost Allocation Part I | • Discuss policy • Present and Discuss Costs allocated Source, Target and Conditions (using DOC cost allocation methodology) • Present and Discuss Cost Allocation Methods: calculation, data elements (ex: specific OC) • Identify Scenarios of Cost Allocation standardization • Discuss Accounting | 2020-10-27 | 1 PM - 3 PM |  | 2 | X | X
| 29 | Pending | 1 | PRISM | Requisition Management Demo | • Structuring line items • Routing to pre-established routing lists • Loading attachments and supporting documents • Sending requisitions to the Unison Marketplace | 2020-10-28 | 1 PM - 3 PM |  | 2 | X | X
| 30 |  | 2 | PRISM | Pre-Solicitation/Solicitation Demo | • Posting a pre-solicitation/sources sought/special notice to FedConnect • Loading clause templates, section templates, cover pages, attachments, and supporting documents • Structuring CLINs (option line items, supplies/services) • Distributing the solicitation to vendors – public vs. directed • Posting the solicitation or combined synopsis/solicitation to FedConnect • Sending the solicitation to a distribution list of users (internal and external to PRISM) • Receiving messages and responses through the FedConnect vendor portal • Creating amendments | 2021-01-12 | 2 PM - 4 PM |  | 2 | X | X
| 31 |  | 2 | PRISM | Pre-Solicitation/Solicitation Workshop | • Determine the following information: - Section and clause templates at an agency level | 2021-01-19 | 1 PM - 5 PM |  | 4 | X | X
| 32 |  | 2 | PRISM | Pre-Solicitation/Solicitation Workshop | • Review section and clause templates at an agency level | 2021-01-25 | 1 PM - 5 PM |  | 4 | X | X
| 33 |  | 2 | PRISM | Pre-Solicitation/Solicitation | • Posting a pre-solicitation/sources sought/special notice to Beta.SAM.gov and FedConnect • Loading clause templates, section templates, cover pages, attachments, and supporting documents • Structuring CLINs (option line items, supplies/services) • Distributing the solicitation to vendors – public vs. directed • Posting the solicitation or combined synopsis/solicitation to FedConnect • Sending the solicitation to a distribution list of users (internal and external to PRISM) • Receiving messages and responses through the FedConnect vendor portal • Creating amendments | 2021-02-03 | 9 AM - 12 PM |  | 3 | X | X | X
| 34 |  | 2 | PRISM | Award Management Demo | • Associating line items to requisitions • Validating the vendor against SAM • Adding clauses and sections • Managing warrants • Loading attachments and supporting documents • Sending the award notice to the vendor in FedConnect • Distributing the award to a list of users (internal and external to PRISM) • Creating additional award types (BPA, BPA call, purchase order, contract, delivery/task order) | 2021-02-08 | 1 PM - 5 PM |  | 4 | X | X
| 35 |  | 3 | PRISM | Award Management Workshop (placeholder if needed) | • Determine the following information: - Custom fields | 2021-02-11 | 9 AM - 11 AM |  | 2 | X | X
| 36 |  | 2 | PRISM | Award Management | • Associating line items to requisitions • Performing a funds check against the financial system • Validating the vendor against SAM • Adding clauses and sections • Managing warrants • Loading attachments and supporting documents • Sending the award notice to the vendor in FedConnect • Distributing the award to a list of users (internal and external to PRISM) • Creating additional award types (BPA, BPA call, purchase order, contract, delivery/task order) | 2021-03-03 | 9 AM - 1 PM |  | 4 | X | X | X
| 37 |  | 3 | PRISM | Post Award Management and Closeout Demo | • Processing funded and unfunded modifications • Sending and receiving files and messages through the FedConnect vendor portal • Loading and completing a closeout checklist • Closing awards in PRISM and FPDS | 2021-04-07 | 9 AM - 11 AM |  | 2 | X | X
| 38 |  | 3 | PRISM | Closeout Workshop | • Determine the following information: - Closeout checklists | 2021-04-14 | 9 AM - 11 AM |  | 2 | X | X
| 39 |  | 3 | PRISM | Post Award Management and Closeout | • Processing funded and unfunded modifications • Sending and receiving files and messages through the FedConnect vendor portal • Loading and completing a closeout checklist • Closing awards in PRISM and FPDS | 2021-05-05 | 9 AM - 11 AM |  | 2 | X | X | X
| 40 |  | 3 | PRISM | Security Group Workshop | • Establish security groups and privileges | 2021-05-19 | 9 AM - 5 PM |  | 8 | X | X
| 41 |  | 3 | PRISM | Security Group Workshop | • Review security groups and privileges • Demonstrate configurations (need to identify system admins if appropriate) | 2021-06-02 | 9 AM - 11 AM |  | 2 | X | X | X
| 42 |  | 3 | PRISM | G Invoicing Approach | Review PRISM Capabilities related to PRISM business process flows | 2021-04-13 | 11 AM - 12 PM |  | 2 | X | X
| 43 |  | 3 | PRISM | G Invoicing Approach | Review PRISM Capabilities related to PRISM business process flows | 2021-05-20 | 11 AM - 12 PM |  | 2 | X | X | X
| 44 |  | 1 | SF Real Property | Review SF Open Requirements | • Review questions on requirements | N/A | N/A
| 45 | Complete | 1 | SF Real Property | Review SF RP Approach | Review Upcoming Meeting Schedule & Flow | 2020-09-17 | 3 PM - 4 PM |  | 1 | X
| 46 | Complete | 1 | SF Real Property | Review SF RP Approach | Review Upcoming Meeting Schedule & Flow | 2020-09-22 | 1 PM - 3 PM |  | 2 | X | X
| 47 | Complete | 1 | SF Real Property | Common Solution Kickoff | Review CS Approach Review SF Navigation if necessary | 2020-09-30 | 1 PM - 3 PM |  | 2 | X | X | X
| 48 | Complete | 1 | SF Real Property | Acquisition (RP) | Current As-Is Acquisition Process System of Record Incorporation Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) | 2020-10-06 | 1 PM - 3 PM |  | 2 | X | X
| 49 | Complete | 1 | SF Real Property | Utilization (RP) | Current As-Is Utilization Process Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | 2020-10-07 | 1 PM - 3 PM |  | 2 | X | X
| 50 | Complete | 1 | SF Real Property | Utilization (RP) | Current As-Is Utilization Process Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | 2020-10-08 | 1 PM - 3 PM |  | 2 | X | X
| 51 | Complete | 1 | SF Real Property | Finance Treatment (RP) | Current As-Is Business Process Review Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress | 2020-10-13 | 1 PM - 3 PM |  | 2 | X | X
| 52 | Complete | 1 | SF Real Property | Finance Treatment (RP) | Current As-Is Business Process Review Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress Leased Assets Treatment Work in Progress Treatment Useful Lifecycle Salvage Value | 2020-10-14 | 1 PM - 3 PM |  | 2 | X | X
| 53 | Pending | 1 | SF Real Property | Utilization (RP) | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | 2020-10-28 | 1 PM - 3 PM |  | 2 | X | X | X
| 54 | Postponed | 1 | SF Real Property | Finance Treatment (RP) | Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress | 2020-10-29 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM | TBD | 4 | X | X | X
| 55 | Postponed | 1 | SF Real Property | Finance Treatment (RP) | Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress Leased Assets Treatment Work in Progress Treatment Useful Lifecycle Salvage Value | 2020-11-03 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM | TBD | 4 | X | X | X
| 56 | Pending | 1 | PRISM | Requisition Management Workshop | • Determine the following information: - Standard requisition numbering masks - Route roles - Additional information to track outside of COTS fields | 2020-11-04 | 9 AM - 1 PM |  | 4 | X | X
| 57 | Cancelled | 1 | SF Real Property | Disposals (RP) | Final Event Types - Disposal Type Final Event User Defined Fields | 2020-11-04 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 58 | Pending | 1 | PTR | Cross Validation Rules | • Review capabilities • Confirm DOC approach | 2020-11-05 | 1 PM - 2 PM |  | 1 | X | X
| 59 | Pending | 2 | SF Real Property | Reporting / Interfaces (RP) | As-Is Reporting Processes As-Is Interfaces & Processed External Reporting Report Needs Disposal FRPP ROW | 2020-11-05 | 1 PM - 3 PM |  | 2 | X | X | X
| 60 | Cancelled | 1 | Projects | Cost Allocation Part II | • Discuss policy • Present and Discuss Costs allocated Source, Target and Conditions (using DOC cost allocation methodology) • Present and Discuss Cost Allocation Methods: calculation, data elements (ex: specific OC) • Identify Scenarios of Cost Allocation standardization • Discuss Accounting | 2020-11-10 | 1 PM - 3 PM | 2020-11-05 | 2 | X | X
| 61 | Pending | 1 | OTC | Billing | • Multi fund AR accounting • Other Accounting requirements • AR Auto accounting • Revenue Recognition rules in AR • Credit Memo approvals | 2020-11-10 | 1 PM - 3 PM |  | 3 | X | X | X
| 62 |  | 2 | SF PP + Fleet | Review SF PP + Fleet Approach | Review Upcoming Meeting Schedule & Flow | 2021-01-06 | 1 PM - 3 PM |  | 2 | X | X
| 63 |  | 2 | SF PP + Fleet | Review SF PP + Fleet Approach | Review Upcoming Meeting Schedule & Flow | 2021-01-13 | 1 PM - 3 PM |  | 2 | X | X
| 64 |  | 2 | SF PP + Fleet | Acquisition PP + Fleet | Current As-IS Acquisition Process Review System of Record Incorporation Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) Owned vs. Leased Assets Software Assets Work in Progress (CIP) Asset Level User Defined Fields Global User Designed Fields | 2021-01-19 | 1 PM - 3 PM |  | 2 | X | X
| 65 |  | 2 | SF PP + Fleet | Utilization PP + Fleet | Current As-Is Utilization Process Role Review & Requirements Work Flow Required Processes Ongoing Events - Asset Transactions Ongoing Events - User Defined Fields Mapped Ongoing Events Requests - Asset Requests Requests - User Defined Fields (Request / Approve) | 2021-01-20 | 1 PM - 3 PM |  | 2 | X | X
| 66 |  | 2 | SF PP + Fleet | Utilization PP + Fleet | Current As-Is Utilization Process Role Review & Requirements Work Flow Required Processes Ongoing Events - Asset Transactions Ongoing Events - User Defined Fields Mapped Ongoing Events Requests - Asset Requests Requests - User Defined Fields (Request / Approve) | 2021-01-21 | 1 PM - 3 PM |  | 2 | X | X
| 67 |  | 2 | SF PP + Fleet | Finance Treatment PP + Fleet | Current As-Is Business Process Review Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Maintenance Cost Treatment Disposals Treatment Leased Assets Treatment Work in Progress Treatment Software Asset Treatment Bulk Purchase Treatment Useful Lifecycle Salvage Value | 2021-01-29 | 1 PM - 3 PM |  | 2 | X | X
| 68 |  | 2 | SF PP + Fleet | Finance Treatment PP + Fleet | Current As-Is Business Process Review Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Maintenance Cost Treatment Disposals Treatment Leased Assets Treatment Work in Progress Treatment Software Asset Treatment Bulk Purchase Treatment Useful Lifecycle Salvage Value | 2021-01-27 | 1 PM - 3 PM |  | 2 | X | X
| 69 |  | 2 | SF PP + Fleet | Disposals PP + Fleet | Current As-Is Business Process Review Final Event Types - Disposal Type Final Event User Defined Fields Identify any processes which may affect Finance Treatment | 2021-01-28 | 1 PM - 3 PM |  | 2 | X | X
| 70 |  | 2 | SF PP + Fleet | Reporting / Interfaces PP + Fleet | As-Is Reporting Processes As-Is Interfaces & Processed External Reporting Report Needs FAST ALD Disposal | 2021-02-02 | 1 PM - 3 PM |  | 2 | X | X
| 71 |  | 2 | SF PP + Fleet | Acquisition PP + Fleet | Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) | 2021-02-03 | 1 PM - 3 PM |  | 4 | X | X | X
| 72 |  | 2 | SF PP + Fleet | Utilization PP + Fleet | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | 2021-02-04 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 73 |  | 2 | SF PP + Fleet | Utilization PP + Fleet | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | 2021-02-09 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 74 |  | 2 | SF PP + Fleet | Finance Treatment PP + Fleet | Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress | 2021-02-10 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 75 |  | 2 | SF PP + Fleet | Finance Treatment PP + Fleet | Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress Leased Assets Treatment Work in Progress Treatment Useful Lifecycle Salvage Value | 2021-02-11 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 76 |  | 2 | SF PP + Fleet | Disposals PP + Fleet | Final Event Types - Disposal Type Final Event User Defined Fields | 2021-02-16 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | 4 | X | X | X
| 77 |  | 2 | SF PP + Fleet | Reporting / Interfaces PP + Fleet | As-Is Reporting Processes As-Is Interfaces & Processed External Reporting Report Needs Disposal FAST VLD Financial Interfaces HR Interfaces | 2021-02-17 | 1 PM - 3 PM |  | 2 | X | X | X
| 78 |  | 1 | PTP | AP Requirements Review | • Review any open requirements required for Common Solution (Receipts, Grants, AP reporting) | N/A | N/A |  |  | X | X
| 79 |  | 3 | PTP | Vendor Management | • Overview of Vendor Maintenance | 2021-05-03 | 1 PM - 2 PM |  | 1 | X | X
| 80 | Pending | 1 | PTP | AP Invoices | • EBS AP Invoice Overview • Approval Hierarchies • Overview of Invoice Entry/Approval Hierarchies/Holds/Adjustment scenarios • Discuss any unique/current business scenarios for Invoice Holds & Adjustments | 2020-11-16 | 1 PM - 3 PM |  | 2 | X | X
| 81 | Cancelled | 1 | Projects | Labor Costs and other External Costs interfaced into Oracle Projects | • Identify Type of Cost (Labor + External Cost) interfaced into PA • Source and target for the integration • Data elements • External costs and accounting | 2020-11-17 | 1 PM - 3 PM | N/A | 2 | X | X
| 82 |  | 3 | PTP | P-Card | • Overview of EBS approval hierarchy capability • Obtain suggestion from Client to what level approval hierarchies will be required | 2021-04-05 | 1 PM - 2 PM |  | 1 | X | X
| 83 |  | 3 | PTP | Travel | • Discussion of unique travel transactions within the DOC | 2021-04-11 | 1 PM - 2 PM |  | 1 | X | X
| 84 |  | 2 | PTP | AP Payments (PAM,DNP) | Confirm payment profiles and business process scenarios | 2021-01-25 | 1 PM - 3 PM |  | 2 | X | X
| 85 |  | 2 | PTP | AP Payments (PAM,DNP) | • Overview of PAM (Payment Automation Manager) - list of DOC TAS/BETCs required • Federal Payment Formats (ACH/Check) • CTA Review (system capabilities) | 2021-03-02 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 86 |  | 3 | PTP | Smart Pay (P-Card/T-Card/Fleet Card Transactions) | • Overview of Oracle EBS P-card/T-card Transactions • Discuss unique/current business scenarios for DOC P-card & T-Card transactions • Overview of CTA (Classification Transactions + Accountability Process) and monthly accounting activity reports to Treasury • CARS enrollment | 2021-05-17 | 1 PM - 3 PM |  | 2 | X | X
| 87 |  | 3 | PTP | Smart Pay (P-Card/T-Card/Fleet Card Transactions) | • Oracle EBS P-card/T-card Transactions • P-card/Travel interface • Discuss unique/current business scenarios for DOC P-card & T-Card transactions • Overview of CTA (Classification Transactions + Accountability Process) and monthly accounting activity reports to Treasury • CARS enrollment | 2021-06-07 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 88 |  | 3 | PTP | Vendor e-Invoicing | • Scope clarification • Confirm business scenarios | 2021-04-25 | 1 PM - 3 PM |  | 2 | X | X
| 89 |  | 3 | PTP | Vendor e-Invoicing | • Overview of capabilities / approach for Vendor E-Portal Requirements • Demonstrate Vendor E-Portal integration | 2021-06-21 | 1 PM - 3 PM |  | 2 | X | X | X
| 90 |  | 3 | PTP | Payroll & Transactions | • Overview of integration to Payroll/Travel modules within Oracle EBS • Discuss current DOC requirements on Payroll practices | 2021-04-05 | 1 PM - 3 PM |  | 2 | X | X | X
| 91 |  | 3 | PTP | Payroll & Transactions | • Overview of integration to Payroll/Travel modules within Oracle EBS • Discuss current DOC requirements on Payroll practices | 2021-06-17 | 1 PM - 3 PM |  | 2 | X | X | X
| 92 |  | 1 | Projects | Project Costing Requirements | Review any open requirements | N/A | N/A |  |  | X | X
| 93 |  | 1 | Projects | Project Billing Requirements | Review any open requirements | N/A | N/A |  |  | X | X
| 94 | Pending | 1 | INT | PRISM/EBS | Dev/Test Environment Connectivity Commitments Obligations Vendor Sync Fund Check | 2020-11-17 | 10 AM - 11 AM |  | 1 | X
| 95 | Pending | 1 | INT | Sunflower/EBS | Dev/Test Environment Connectivity Mass Asset Addition Sunflower Financial to EBS | 2020-11-19 | 10 AM - 11 AM |  | 1 | X
| 96 | Cancelled | 3 | Projects | Accounting in Projects | • Review of the accounting generated in Projects • Accounting for costs (Burden, allocations) • Accounting for Revenue and Invoices | 2020-11-24 | 1 PM - 3 PM | N/A | 2 | X | X
| 97 |  | 3 | Projects | Reporting and Analysis | • Discuss DOC reporting and analysis needs from policy • Provide Overview of available reports in Projects Costing and Billing | 2021-04-13 | 1 PM - 3 PM |  | 2 | X | X
| 98 |  | 3 | Projects | Reporting and Analysis | • DOC reporting and analysis needs • Provide Overview of available reports in Projects Costing and Billing | 2021-06-15 | 1 PM - 3 PM |  | 2 | X | X | X
| 99 | Complete | 1 | Projects | Data Standardization | • Understand and Discuss DOC documentation on data standardization needs • Collaborate with DOC stakeholders on communicating policy | 2020-10-08 | 1 PM - 3 PM |  | 2 | X | X
| 100 | Pending | 1 | PTR | Cross Validation Rules | • Review capabilities • Demonstrate Cross Validation impact transactional level | 2020-12-01 | 1 PM - 3 PM |  | 2 | X | X | X
| 101 | Pending | 1 | PRISM | Advanced Acquisition Planning | • Building collaborative acquisition workspaces based on pre-defined templates • Adding, revising, and searching internal notes • Establishing and managing integrated project teams • Tracking acquisition-related data • Developing vendor deliverable schedules • Establishing acquisition milestone schedules • Developing acquisition packages using Microsoft Word and PDF templates • Generating an electronic contract file folder structure • Budget planning for year-over-year commitments and obligations | 2020-12-08 | 9 AM - 1 PM |  | 4 | X | X | X
| 102 | Pending | 1 | Projects | Project Basics | • Review Project Number and Task Number standardization • Review Project Types and Templates | 2020-12-08 | 1 PM - 3 PM | N/A | 2 | X | X | X
| 103 | Pending | 1 | PTR | Ledger Overview | • Overview of the single consolidated DOC Ledger approach • Data Access Control functionality • Operating Units | 2020-12-10 | 1 PM - 3 PM |  | 2 | X | X | X
| 104 |  | 2 | Projects | G-Invoicing - GT&C Process | High level overview related to: •GT&C Process in G-Invoicing and at the Servicing Agency •IAA Process for Receiving Agency | 2021-02-25 | 1 PM - 3 PM |  | 2 |  | X | X
| 105 |  | 3 | Projects | Interagency Agreements​ (Non-Advance): Servicing Agency | Review Policies related to IAA • Enter Agreement without Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | 2021-03-18 | 1 PM - 3 PM |  | 2 | X | X
| 106 |  | 3 | Projects | Interagency Agreements​ (Non-Advance): Servicing Agency | • Enter Agreement without Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | 2021-04-15 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 107 |  | 3 | Projects | Create Funding and Generate Billing and Revenue (Non-Advance) | • Identify scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting • Recording ACR​ | 2021-05-11 | 1 PM - 3 PM |  | 2 | X | X
| 108 |  | 3 | Projects | Create Funding and Generate Billing and Revenue (Non-Advance) | • Review scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting • Recording ACR​ | 2021-06-10 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 109 |  | 4 | Projects | Interagency Agreements (Advance): Servicing Agency | • Enter Agreement with Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification current business cases for IAA With-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Accounting • Capturing Performance Period and Budget Period for Incoming IAAs | 2021-06-24 | 1 PM - 3 PM |  | 2 | X | X
| 110 |  | 4 | Projects | Creating Interagency Agreements (Advance) | • Enter Agreement with Advance (Federal Customer)​ • Agreement fields (Mapping..) • Review current business cases for IAA With-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Accounting • Capturing Performance Period and Budget Period for Incoming IAAs | 2021-07-15 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 111 |  | 4 | Projects | Create Funding and Generate Billing and Revenue (With Advance) | • Identify scenarios of Funding Reimbursable IAA with Advance • Recognize Revenue and Billing : Billing method and process • Billing and Revenue: Accounting • Recording ACR​ | 2021-07-29 | 1 PM - 3 PM |  | 2 | X | X
| 112 |  | 4 | Projects | Create Funding and Generate Billing and Revenue (With Advance) | • Review scenarios of Funding Reimbursable IAA with Advance • Recognize Revenue and Billing : Billing method and process • Billing and Revenue: Accounting • Recording ACR​ | 2021-08-12 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 113 |  | 3 | Projects | Record Advances and Expenditures​ | DOC Policy related to: • Track Task Orders Against Agreements​ • Record Advances against Incoming IAAs​ • Track and Report Liquidation of Advances | 2021-05-18 | 1 PM - 3 PM |  | 2 | X | X
| 114 | Pending | 1 | PRISM | Requisition Management | • Structuring line items • Performing a funds check • Routing to pre-established routing lists • Loading attachments and supporting documents • Sending requisitions to the Unison Marketplace | 2020-12-10 | 9 AM - 12 PM |  | 3 | X | X | X
| 115 |  | 1 | OTC | AR Requirements | Review any open requirements | N/A | N/A |  |  | X | X
| 116 | Complete | 1 | OTC | Customers | • Customer Creation maintenance and sources of customers • Customer Advances • Customer Holds • Confirm reporting requirements from COTS | 2020-10-13 | 1 PM - 3 PM |  | 2 | X | X
| 117 | Pending | 1 | OTC | Policy Meeting: Reimbursable Agreements | • Understand and discuss current DOC policies and practices on reimbursable agreements and adjustments to Project transactions and credit memo creation in AR | 2020-10-19 | 1 PM - 3 PM |  | 2 | X | X
| 118 | Pending | 1 | Projects | Object Classes | • Review Standard Object Classes in Oracle Projects • Review DOC specific Object Classes and Accounting | 2020-12-10 | 1 PM - 3 PM |  | 2 | X | X | X
| 119 | Pending | 1 | PTP | AP Invoices | • EBS AP Invoice and Grants Demo • Overview of Invoice Entry/Approval Hierarchies/Holds/Adjustment scenarios • Discuss any unique/current business scenarios for Invoice Holds & Adjustments | 2020-12-14 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 120 |  | 2 | OTC | Reporting and Analysis | • Overview of standard receivables reports • Generate Standard Receivables Reports • Review Standard Receivables Reports • Confirm reporting requirements from COTS | 2021-01-05 | 1 PM - 3 PM |  | 2 | X | X
| 121 |  | 2 | OTC | Reporting and Analysis | • Overview of standard receivables reports • Generate Standard Receivables Reports • Review Standard Receivables Reports | 2021-03-10 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 122 |  | 2 | OTC | Receipts and Collections | Review DOC standards / approach / policies related to • Create Manual Bill (Invoice) • Create and Apply Receipts • Maintain Unapplied Receipts | 2021-01-08 | 1 PM - 3 PM |  | 2 | X | X
| 123 |  | 2 | OTC | Receipts and Collections | • Create Manual Bill (Invoice) • Create and Apply Receipts • Maintain Unapplied Receipts Dunning Process and Delinquent debt referral | 2021-03-04 | 1 PM - 3 PM |  | 2 | X | X | X
| 124 |  | 2 | OTC | Adjustments | Review DOC standards / approach / policies related to • Apply Debit and Credit Memos • Reversal of a Receipt • Outstanding Receivable Balances (write-offs, debts, interest) | 2021-01-12 | 1 PM - 3 PM |  | 2 | X | X
| 125 |  | 2 | OTC | Adjustments | • Apply Debit and Credit Memos • Reversal of a Receipt • Outstanding Receivable Balances (write-offs, debts, interest) | 2021-03-03 | 9 AM - 12 PM |  | 3 | X | X | X
| 126 |  | 3 | Project/OTC | Federal Interfaces (G-invoicing, IPAC integration and pay.gov) | • Provide overview of key federal interfaces • Discuss current DOC business processes (CIR, pay.gov, etc.) | 2021-05-03 | 1 PM - 3 PM |  | 2 | X | X
| 127 |  | 3 | Project/OTC | Federal Interfaces (G-invoicing, IPAC integration and pay.gov) | • Provide overview of key federal interfaces • Discuss current DOC business processes (CIR, pay.gov, etc.) | 2021-06-02 | 1 PM - 3 PM |  | 2 | X | X | X
| 128 |  | 3 | OTC | IPAC Processing | Review DOC standards / approach / policies related to • IPAC Payment and Collection Processing​ • Billing of Sensitive Agencies​ • Record IPAC Chargebacks | 2021-04-08 | 1 PM - 4 PM |  | 3 | X | X
| 129 |  | 3 | OTC | IPAC Processing | • IPAC Payment and Collection Processing​ • Billing of Sensitive Agencies​ • Record IPAC Chargebacks | 2021-06-09 | 1 PM - 3 PM |  | 2 | X | X | X
| 130 |  | 3 | OTC | Consolidated Billing | Review DOC standards / approach / policies related to Consolidation of Invoices | 2021-04-15 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X
| 131 |  | 3 | OTC | Consolidated Billing | • Consolidation of Invoices | 2021-06-02 | 1 PM - 3 PM |  | 2 | X | X | X
| 132 |  | 2 | INT | CWT Travel | Dev/Test Environment Connectivity Travel Authorizations Travel Vouchers Accounting Strings Employee (Traveler) Record CBA Load | 2021-02-09 | 10 AM - 11 AM |  | 1 | X | X
| 133 |  | 2 | INT | GOL/ASAP | Dev/Test Environment Connectivity Commitments Obligations ASAP Authorization ASAP Treasury Draw Grantee Management/SAM Record Approval Workflow | 2021-03-09 | 10 AM - 11 AM |  | 1 | X | X
| 134 |  | 2 | INT | GMIS/ASAP | Dev/Test Environment Connectivity Commitments Obligations ASAP Authorization ASAP Treasury Draw Grantee Management/SAM Record Approval Workflow | 2021-03-11 | 10 AM - 11 AM |  | 1 | X | X
| 135 |  | 2 | INT | SmartPay | Purchase/Travel/Fleet Transactions Data File Type Connectivity Reconciliation (to Project, ACS, PO) Pay Invoice Clearing Invoice | 2021-01-19 | 10 AM - 11 AM |  | 1 | X | X
| 136 |  | 3 | INT | HFM | Financial Statement Data Extract Requirement BAS Financials/EDW Considerations | 2021-06-08 | 10 AM - 11 AM |  | 1 | X | X
| 137 |  | 3 | INT | NFC | Master Employee Record NFC Payroll Payroll Estimate USCG Payroll Decennial Payroll | 2021-04-29 | 10 AM - 11 AM |  | 1 | X | X
| 138 |  | 3 | INT | Pay.gov, NOAA | Collections Information Repository (CIR) Seafood Acceptance System | 2021-05-11 | 10 AM - 11 AM |  | 1 | X | X
| 139 |  | 3 | INT | Pay.gov, NIST | Standard Reference Data (SRD) Baldridge Salesforce Calibration Payment Misc. Payment | 2021-05-11 | 1 PM - 2 PM |  | 1 | X | X
| 140 |  | 3 | INT | Pay.gov, Census | Data Sales Interface (DSI) | 2021-05-13 | 10 AM - 11 AM |  | 1 | X | X
| 141 |  | 2 | INT | Treasury PAM, DoNotPay | Payment Format: CTX, PPDP, CCDP DNP Vendor list Connectivity | 2021-01-12 | 10 AM - 11 AM |  | 1 | X | X
| 142 |  | 1 | INT | SAM | SAM monthly file (initial load) SAM daily file (incremental load) Connectivity Vendor Management | 2021-01-22 | 10 AM - 11 AM |  | 1 | X
| 143 |  | 3 | INT | MoveLINQ | Dev/Test Environment Connectivity Relocation Authorizations Relocation Vouchers Accounting Strings Employee Record | 2021-06-08 | 10 AM - 11 AM |  | 1 | X | X
| 144 |  | TBD | INT | PTP Other: NOAA Specific | OPCS Express Small Package System SF270 Invoice Processing GSA Motor Pool Telecom Charges other NOAA PTP interfaces | TBD | TBD |  | 1 | X | X
+ | 145 |  | TBD | INT | OTC Other: NOAA Specific | NDW extract applications other NOAA OTC interfaces | TBD | TBD |  | 1 | X | X
| 146 |  | TBD | INT | PTR Other: NOAA Specific | other NOAA PTR interfaces | TBD | TBD |  | 1 | X | X
| 147 |  | TBD | INT | NOAA Specific Other | All other interfaces for BAS consideration | TBD | TBD |  | 1 | X | X
| 148 |  | TBD | INT | PTP Other: NIST Specific | American Bankers Association Facilities PO Government Bill of Landing other NIST PTP interfaces | TBD | TBD |  | 1 | X | X
| 149 |  | TBD | INT | OTC Other: NIST Specific | ITA Safe Harbor ITA eMenu OS WCF unbilled collections other NIST OTC interfaces | TBD | TBD |  | 1 | X | X
| 150 |  | TBD | INT | PTR Other: NIST Specific | Administrative Services Division Boulder Plant charges Cryptographic module validation program Department of State interface ITA centralized services Plant Gaithersburg Washington interagency telecommunication services other NIST PTR interfaces | TBD | TBD |  | 1 | X | X
| 151 |  | TBD | INT | NIST Specific Other | Maximo ANTS property All other interfaces for BAS consideration | TBD | TBD |  | 1 | X | X
| 152 |  | TBD | INT | PTP Other: Census Specific | Cost and Response Management Network (CARMIN) Census Printing Management System (CPMS) Express Small Package System (ESPS) Education & Training Management System (ETMIS) IT Business Plan (ITBP)/CAT Postal Transportation Apps ( Carpool, Parking & Subsidy) Other Census PTP interfaces | TBD | TBD |  | 1 | X | X
| 153 |  | TBD | INT | OTC Other: Census Specific | Jeffersonville Time and Attendance System (JTAS) Jeffersonville Activity Reporting System (JARS) Cost Activity Reporting System (CARS) Overtime Authorization Request System (OAR+) T&A Validation Other Census OTC interfaces | TBD | TBD |  | 1 | X | X
| 154 |  | TBD | INT | PTR Other: Census Specific | Consolidated Budget Reporting and Analysis (COBRA) Internal Cost Distribution System (ICDS) Other Census PTR interfaces | TBD | TBD |  | 1 | X | X
| 155 |  | TBD | INT | Census Specific Other | ATRAK CAMPIN Hazardous Materials Tracking (HMT) James Bond Identification (JBOND) PEARS PTCS Safety Monitor Reporting System (SMRS) Unified Tracking System (UTS) All other interfaces for BAS consideration | TBD | TBD |  | 1 | X | X
| 156 | Pending | 1 | Projects | Cost Allocation | •Present and Discuss Costs allocated Source, Target and Conditions (using DOC cost allocation methodology) • Present and Discuss Cost Allocation Methods: calculation, data elements (ex: specific OC) • Identify Scenarios of Cost Allocation standardization • Discuss Accounting | 2020-12-15 | 10 AM - 12 PM 1 PM - 3 PM |  | 4 | X | X | X
| 157 | Cancelled | 1 | Projects | Labor Costs and other External Costs interfaced into Oracle Projects | • Identify Type of Cost (Labor + External Cost) interfaced into PA • Source and target for the integration • Data elements • External costs and accounting | 2020-12-17 | 1 PM - 3 PM | N/A | 2 | X | X | X
| 158 | Complete | 1 | All | Review CS Kickoff | Review CS Kickoff Materials | 2020-09-23 | 11 AM - 12 PM |  | 1 | X
| 159 | Complete | 1 | All | Common Solution Kickoff (1) | Review CS Approach Review SF Navigation if necessary Focus is Acquisition / Financials | 2020-10-01 | 1 PM - 3 PM |  | 2 | X | X | X
| 160 | Complete | 1 | All | Common Solution Kickoff (2) | Review CS Approach Review SF Navigation if necessary Focus is Acquisition / Financials | 2020-10-07 | 10 AM - 12 PM 1 PM - 3 PM |  | 2 | X | X | X
| 161 | Cancelled | 1 | Projects | Object Classes | • Standard Object Classes in Oracle Projects • DOC specific Object Classes and Accounting | 2020-10-15 | 1 PM - 3 PM |  | 2 | X | X
| 162 | Pending | 1 | Projects | Object Classes | • Standard Object Classes in Oracle Projects • DOC specific Object Classes and Accounting | N/A | 11 AM - 12 PM | 2020-10-23 | 1
| 163 | Complete | 1 | PTP | Vendor e-Invoicing | • Overview of capabilities / approach for Vendor E-Portal Requirements • Provide capabilities / approach for Vendor E-Portal Requirements | 2020-10-15 | 1 PM - 3 PM |  | 2 | X | X
| 164 | Pending | 1 | PTP | Vendor e-Invoicing | • Overview of capabilities / approach for Vendor E-Portal Requirements • Provide capabilities / approach for Vendor E-Portal Requirements | N/A | 1 PM - 3 PM | 2020-10-28 | 2
| 165 | Pending | 1 | SF Real Property | Acquisitions/Utilization | Energy Savings Performance Contracts Operating & Maintenance Costs Space Details Assessments & Surveys Lease Charges Project & Management Tracking | N/A | 1 PM - 3 PM | 2020-10-29 | 2 | X | X
| 166 | Pending | 1 | SF Real Property | Finance | CWIP Capital Leases Reporting Bureau vs. Occupying Bureau Projected Depreciation for Reporting TR-14 Disposal Process Access Database / Activity Tracking by Task Code Capitalization for building improvements that follow a different useful life depreciation schedule Historical Status Impairment Discussions Accounting Treatments Rent on the Web | N/A | 11 AM - 1 PM | 2020-11-06 | 2 | X | X
Note on F98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hanayen, Rafaat [i360Technologies Inc] @Smirniotopoulos, Jennifer Does this need a session with the full CS in month 3? Reply: Raf wanted to do this session in November to give some buffer time to understand the implication(s) of g-invoicing on revenue and other aspects (after the first set of patches in October).