## Calendar 4.0 (hidden)
| # | CAROL ACTION | Revised | Status | Sprint | Workstream | Focus Area | Key Topics | Month | Original Date | Preferred Time | Revised Date | Revised Details | Duration (Hours) | AFS EXEC | AFS POC | DOC BAS PMO | Decision Making Forum | CS Participants | Policy | BAS Strategy | Deep Dives | Configuration Validation | Comments | Carol
| 164E | Y | Y | Pending | 2 | SYS | SYS RBAC Discussion | Review roles and responsibilities for Sys Admin (Oracle) |  | 2021-02-08 | 1 PM - 3 PM |  | 2020-02-10 | 2 | Mary Beth Torpey | Tracey Carpenter | X | X |  |  |  | X
| 102B | N | Y | Pending | 1 | Projects | Object Classes | • Standard Object Classes in Oracle Projects • DOC specific Object Classes and Accounting |  | N/A | 11 AM - 12 PM |  | 2020-10-23 | 1 | Tracey Carpenter | Jenn Smirniotopoulos | [7 empty] | New meeting with BAS PMO audience (+Jen, Lynn); already scheduled by MBT
| 80B | N | Y | Pending | 1 | PTP | Vendor e-Invoicing | • Overview of capabilities / approach for Vendor E-Portal Requirements • Provide capabilities / approach for Vendor E-Portal Requirements |  | N/A | 1 PM - 3 PM |  | 2020-10-28 | 2 | Mary Beth Torpey | Loda Opot | [7 empty] | Meeting only with Karen to understand IPP better from a Functional Design perspective; Change audience (cancelled for larger audience); already scheduled by MBT
| 58B | Y | N/A | Complete | 1 | SF Real Property | SF Real Property Acquisition and Utilization | Energy Savings Performance Contracts Operating & Maintenance Costs Space Details Assessments & Surveys Lease Charges Project & Management Tracking Replacement Valuation & Repair Needs Calculations |  | N/A | 1 PM - 3 PM |  | 2020-10-29 | 2
| 96 | N | Y | Cancelled | 1 | Projects | Cost Allocation Part II | • Discuss policy • Present and Discuss Costs allocated Source, Target and Conditions (using DOC cost allocation methodology) • Present and Discuss Cost Allocation Methods: calculation, data elements (ex: specific OC) • Identify Scenarios of Cost Allocation standardization • Discuss Accounting | November | 2020-11-10 | 1 PM - 3 PM |  | 2020-11-05 | 2 |  |  | X | X |  | X |  | X |  | Cancelled for larger audience - need to create session with smaller group with BAS PMO (including initial questions via email as appropriate); MBT to coordinate | Canceled
| 61B | Y | Y | Complete | 1 | SF Real Property | SF Real Property Finance Treatment | CWIP Capital Leases Reporting Bureau vs. Occupying Bureau Projected Depreciation for Reporting TR-14 Disposal Process Access Database / Activity Tracking by Task Code Capitalization for building improvements that follow a different useful life depreciation schedule Historical Status Impairment Discussions Accounting Treatments Rent on the Web |  | N/A | 11 AM - 1 PM |  | 2020-11-06 | 2
| 62A | N | Y | Cancelled | 2 | SF PP + Fleet | Review SF PP + Fleet Approach | Review Upcoming Meeting Schedule & Flow | January | 2021-01-06 | 1 PM - 3 PM |  | 2021-01-06 | 2 | Mary Beth Torpey | Mike Tanner | X |  |  | X | X | X |  | Internal meeting with BAS PMO | Y
| 13A | N | N/A | Scheduled | 2 | PTR | Budget Entry/Funds Status Report | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report | January | 2021-01-07 | 1 PM - 1:30 PM |  | 2021-01-07 | 0.5 | Mary Beth Torpey | Darsh Patel | X |  |  |  | X |  |  | Internal meeting with BAS PMO | Y
| 30A | N | Y | Scheduled | 2 | PRISM | Pre-Solicitation/Solicitation Demo | • Posting a pre-solicitation/sources sought/special notice to FedConnect • Loading clause templates, section templates, cover pages, attachments, and supporting documents • Structuring CLINs (option line items, supplies/services) • Distributing the solicitation to vendors – public vs. directed • Posting the solicitation or combined synopsis/solicitation to FedConnect • Sending the solicitation to a distribution list of users (internal and external to PRISM) • Receiving messages and responses through the FedConnect vendor portal • Creating amendments | January | 2021-01-07 | 11:00 - 11:30 AM |  | 2021-01-07 | 0.5 |  |  | X | [6 empty] | Internal meeting with BAS PMO | Y
| 163A | Cancelled | Y | Cancelled | 2 | PTR | ACS Review Part 1 | Review of ACS Segments Standardization of Segment Value | Review of ACS Segments Standardization of Segment Value | 2021-01-07 | 2 PM - 4 PM |  | 2021-01-07 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  | X
| 124A | N | Y | Scheduled | 2 | OTC | Receipts and Collections | Review DOC standards / approach / policies related to • Create Manual Bill (Invoice) • Create and Apply Receipts • Maintain Unapplied Receipts | January | 2021-01-11 | 1 PM - 1:30 PM |  | 2021-01-11 | 0.5 |  |  | X |  |  |  | X |  |  | Internal meeting with BAS PMO | Y
| 30B | N | Y | Scheduled | 2 | PRISM | Pre-Solicitation/Solicitation Demo | • Posting a pre-solicitation/sources sought/special notice to FedConnect • Loading clause templates, section templates, cover pages, attachments, and supporting documents • Structuring CLINs (option line items, supplies/services) • Distributing the solicitation to vendors – public vs. directed • Posting the solicitation or combined synopsis/solicitation to FedConnect • Sending the solicitation to a distribution list of users (internal and external to PRISM) • Receiving messages and responses through the FedConnect vendor portal • Creating amendments |  | 2021-01-12 | 1 PM - 3 PM |  | 2021-01-12 | 2 | Mary Beth Torpey | Molly Brewer | X | X |  | X |  | X
| 63 | N | N/A | Cancelled | 2 | SF PP + Fleet | Review SF PP + Fleet Approach | Review Upcoming Meeting Schedule & Flow | January | 2021-01-13 | 1 PM - 3 PM |  | 2021-01-13 | 2 | Mike Tanner / MBT | Danielle Lyon | X |  |  |  | X |  |  | Internal meeting with BAS PMO | Y
| 13B | N | N/A | Scheduled | 2 | PTR | Budget Entry/Funds Status Report | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report |  | 2021-01-14 | 1 PM - 3 PM |  | 2021-01-14 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  | X | X | X
| 31 | N | N/A | Scheduled | 2 | PRISM | Pre-Solicitation/Solicitation Workshop | • Determine the following information: - Section and clause templates at an agency level | January | 2021-01-19 | 1 PM - 5 PM |  | 2021-01-19 | 4 | Mary Beth Torpey | Molly Brewer | X | X |  | X |  | X |  |  | Y
| 85A | N |  | Pending | 2 | PTP | AP Payments (PAM,DNP) | Confirm payment profiles and business process scenarios | January | 2021-01-20 | 10:30 AM - 11 AM |  | 2021-01-21 | 0.5 | Mary Beth Torpey | Loda Opot | X |  |  |  | X |  |  | Internal meeting with BAS PMO | Y
| 164D | Y | Y | Pending | 2 | SYS | SYS RBAC Discussion | Review roles and responsibilities for Sys Admin (Oracle) | 2021-02-08 | 2020-01-21 | 1 PM - 3 PM |  | 2021-01-21 | 2 | Mary Beth Torpey | Tracey Carpenter | X |  | X |  |  |  |  | Internal meeting with BAS PMO
| 126A | N | Y | Scheduled | 2 | OTC | Adjustments | Review DOC standards / approach / policies related to • Apply Debit and Credit Memos • Reversal of a Receipt • Outstanding Receivable Balances (write-offs, debts, interest) | January | 2021-01-20 | 9 AM - 9:30AM |  | 2021-01-20 | 0.5 | Mary Beth Torpey | Jenn Smirniotopoulos | X |  |  | X | X |  |  | Internal meeting with BAS PMO | Y
| 144 | Y |  | Pending | 2 | INT | SAM | SAM monthly file (initial load) SAM daily file (incremental load) Connectivity Vendor Management | December | 2021-01-22 | 11 AM - 12 PM |  | 2021-01-22 | 1 | Jae Lee | Phyllis Keehn | X | [6 empty] | This will be an internal meeting to go over SAM interface designs | Y
| 124B | N | Y | Scheduled | 2 | OTC | Receipts and Collections | Review DOC standards / approach / policies related to • Create Manual Bill (Invoice) • Create and Apply Receipts • Maintain Unapplied Receipts | January | 2021-01-08 | 1 PM - 3 PM |  | 2021-01-22 | 2 | Mary Beth Torpey | Jenn Smirniotopoulos | X | X |  | X |  | X
| 163B | N | Y | Scheduled | 2 | PTR | ACS Review Part 1 | - Agency, Fund, BFY, Bureau, Program |  | 2021-01-25 | 10 AM - 12 PM |  | 2021-01-25 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  | X
| 163C | N | Y | Scheduled | 2 | PTR | ACS Review Part 2 | - Org, Object Class, USSGL |  |  | 2 PM - 4 PM |  | 2021-02-16 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  | X
| 163D | Y | Y | Pending | 2 | PTR | ACS and Project / Task | • Project and Task • Project and Task and BAS ACS Integration |  |  | 1 PM - 3PM |  | 2021-03-31 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  | X
| 126B | N | Y | Scheduled | 2 | OTC | Adjustments | Review DOC standards / approach / policies related to • Apply Debit and Credit Memos • Reversal of a Receipt • Outstanding Receivable Balances (write-offs, debts, interest) | January | 2021-01-12 | 1 PM - 3 PM |  | 2021-01-25 | 2 | Mary Beth Torpey | Jenn Smirniotopoulos | X | X |  | X | X | X
| 85B | N | Y | Scheduled | 2 | PTP | AP Payments (PAM,DNP) | Confirm payment profiles and business process scenarios |  | 2021-01-25 | 10 AM - 12 PM |  | 2021-01-26 | 2 | Mary Beth Torpey | Loda Opot | X | X |  | X |  | X
| 32 | N |  | Scheduled | 2 | PRISM | Pre-Solicitation/Solicitation Workshop | • Review section and clause templates at an agency level | January | 2021-01-25 | 1 PM - 5 PM |  | 2021-01-27 | 4 | Mary Beth Torpey | Molly Brewer | X | X |  | X |  | X |  |  | Y
| 165 | Y | Y | Pending | 2 | All | Sprint 1 Closeout + Sprint 2 Kickoff | Review Sprint 1 Outcomes Highlight Sprint 2 Objectives |  | 2021-01-21 | 1 PM - 3 PM |  | 2021-01-28 | 2 | Mary Beth Torpey |  | X | X |  |  |  | X
| 164A | Y | Y | Pending | 2 | PTP | PTP RBAC Discussion | Review roles and responsibilities for PO, AP, Payments, Project Costing |  | 2021-01-29 | 1 PM - 3 PM |  | 2021-01-29 | 2 | Mary Beth Torpey | Tracey Carpenter | X | X |  |  |  | X
| 164B | Y | Y | Pending | 2 | OTC | OTC RBAC Discussion | Review roles and responsibilities for AR, Project Billing | February | 2021-02-01 | 1 PM - 3 PM |  | 2021-02-01 | 2 | Mary Beth Torpey | Tracey Carpenter | X | X |  |  |  | X
| 34A | N |  | Scheduled | 2 | PRISM | Award Management Demo | • Associating line items to requisitions • Validating the vendor against SAM • Adding clauses and sections • Managing warrants • Loading attachments and supporting documents • Sending the award notice to the vendor in FedConnect • Distributing the award to a list of users (internal and external to PRISM) • Creating additional award types (BPA, BPA call, purchase order, contract, delivery/task order) | February | 2021-02-08 | 10 AM - 10:30 AM |  | 2021-02-03 | 0.5 | Mary Beth Torpey | Molly Brewer | X |  |  |  | X |  |  | Internal meeting with BAS PMO | Y
| 122 | N | Y | Scheduled | 2 | OTC | Reporting and Analysis | • Overview of standard receivables reports • Generate Standard Receivables Reports • Review Standard Receivables Reports • Confirm reporting requirements from COTS | February | 2021-01-05 | 1 PM - 3 PM |  | 2021-02-04 | 2 | Mary Beth Torpey | Jenn Smirniotopoulos |  | X |  | X |  | X |  | Push out to February to provide more time for internal review before regrouping with DMF | Y
| 164C | Y | Y | Pending | 2 | PTR | PTR RBAC Discussion | Review roles and responsibilities for GL, FV |  | 2021-02-05 | 1 PM - 3 PM |  | 2021-02-05 | 2 | Mary Beth Torpey | Tracey Carpenter | X | X |  |  |  | X
| 34B | N |  | Scheduled | 2 | PRISM | Award Management Demo | ab | February | 2021-02-08 | 1 PM - 5 PM |  | 2021-02-08 | 4 | Mary Beth Torpey | Molly Brewer | X | X |  | X |  | X |  |  | Y
| 13C | Y | N/A | Pending | 2 | PTR | Budget Entry/Funds Status Report Follow Up | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report |  | 2021-02-09 | 1 PM - 3 PM |  | 2021-02-24 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  | X
| 134 | Y | Y | Pending | 2 | INT | CWT Travel | Dev/Test Environment Connectivity Travel Authorizations Travel Vouchers Accounting Strings Employee (Traveler) Record CBA Load | February | 2021-02-09 | 10 AM - 11 AM |  | 2021-02-09 | 1 | JAe Lee | Phyllis Keehn | X | [6 empty] | Internal Design Session | Y
| 35 | Y |  | Scheduled | 2 | PRISM | Award Management Workshop (placeholder if needed) | • Determine the following information: - Custom fields | February | 2021-02-11 | 1 PM - 3PM |  | 2021-02-11 | 2 | Mary Beth Torpey | Molly Brewer | X | X |  | X |  | X | X |  | Y
| 106A | Y | Y | Cancelled | 2 | Projects | G-Invoicing - GT&C Process | High level overview related to: •GT&C Process in G-Invoicing and at the Servicing Agency •IAA Process for Receiving Agency | February | 2021-02-25 | 1 PM - 3 PM |  | 2021-02-17 | 2 | Mary Beth Torpey | Phyllis Keehn | X |  |  |  | X |  |  | Internal meeting with BAS PMO | Y
| 137 | Y | N/A | Pending | 2 | INT | SmartPay | Purchase/Travel/Fleet Transactions Data File Type Connectivity Reconciliation (to Project, ACS, PO) Pay Invoice Clearing Invoice | January | 2021-01-19 | 10 AM - 11 AM |  | 2021-02-23 | 1 | Jae Lee | Phyllis Keehn | X | [6 empty] | Internal Design Session, Updated preferred date | Y
| 9A | Y | Y | Pending | 2 | PTR | Journal Approval Workflow/ Reversal (Manual) | • Auto Reversal • Manual-Entry Journal Reversal • Single - Entry Reversal business scenarios • Journal Approval Process Walkthrough • Approver Hierarchy • Email Notifications to preparer/approver | March | 2021-02-24 | 10 AM - 12 PM |  | 2021-02-10 | 2 | Mary Beth Torpey | Darsh Patel | X |  |  |  | X |  |  | Internal meeting with BAS PMO
| 106B | Y | Y | Pending | 2 | Projects | G-Invoicing - GT&C Process | High level overview related to: •GT&C Process in G-Invoicing and at the Servicing Agency •IAA Process for Receiving Agency | February | 2021-02-25 | 1 PM - 3 PM |  | 2021-03-08 | 2 | Mary Beth Torpey | Phyllis Keehn | X | X |  | X | X | X |  | Jenn and Raf recommend moving this to 3 hours | Y
| 9B | N | Y | Cancelled | 2 | PTR | Journal Approval Workflow/ Reversal (Manual) | • Journal Approval Process Walkthrough • Approver Hierarchy • Email Notifications to preparer/approver | March | 2021-03-02 | 1 PM - 3 PM |  | 2021-03-04 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  |  | X | Assumes no deep dive required that this can be provide to the communities based on confirmation via email of the required workflow | Y
| 86 | Y | N/A | Pending | 2 | PTP | AP Payments (PAM,DNP) | • Overview of PAM (Payment Automation Manager) - list of DOC TAS/BETCs required • Federal Payment Formats (ACH/Check) • CTA Review (system capabilities) | March | 2021-03-02 | 10 AM - 12 PM 1 PM - 3 PM |  | 2021-03-02 | 4 | Mary Beth Torpey | Loda Opot | X | X |  |  |  |  | X |  | Y
| 143 | Y | N/A | Pending | 2 | INT | Treasury PAM, DoNotPay | Payment Format: CTX, PPDP, CCDP DNP Vendor list Connectivity | January | 2021-01-12 | 10 AM - 11 AM |  | 2021-03-02 | 1 | Jae Lee | Phyllis Keehn | X | [6 empty] | Internal Design Session, Updated preferred date | Y
| 33 | Y | Y | Pending | 2 | PRISM | Pre-Solicitation/Solicitation | • Posting a pre-solicitation/sources sought/special notice to Beta.SAM.gov and FedConnect • Loading clause templates, section templates, cover pages, attachments, and supporting documents • Structuring CLINs (option line items, supplies/services) • Distributing the solicitation to vendors – public vs. directed • Posting the solicitation or combined synopsis/solicitation to FedConnect • Sending the solicitation to a distribution list of users (internal and external to PRISM) • Receiving messages and responses through the FedConnect vendor portal • Creating amendments | February | 2021-02-03 | 1 PM - 4 PM |  | 2021-03-03 | 3 | Mary Beth Torpey | Molly Brewer | X | X |  |  |  |  | X | Updated time to reflect West Coast time zones | Y
| 127 | Y | Y | Pending | 2 | OTC | Adjustments | • Apply Debit and Credit Memos • Reversal of a Receipt • Outstanding Receivable Balances (write-offs, debts, interest) | March | 2021-03-03 | 1 - 4 PM |  | 2021-03-04 | 3 | Mary Beth Torpey | Jenn Smirniotopoulos | X | X |  |  |  |  | X |  | Y
| 10A | Y | N/A | Pending | 2 | PTR | Journal Approval Workflow/ Reversal (Manual) | • Auto Reversal • Manual-Entry Journal Reversal • Single - Entry Reversal business scenarios • Journal Approval Process Walkthrough • Approver Hierarchy • Email Notifications to preparer/approver | March | 2021-03-04 | 10 AM - 12 PM |  | 2021-03-01 | 2 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  |  | X |  | Y
| 107A | N | Y | Pending | 3 | Projects | (GINV) Interagency Agreements​: Servicing Agency | Review Policies related to IAA • Enter Agreement without Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | April | 2021-03-04 | 1 PM - 2 PM | 2021-04-12 | Push to April | 1 | Mary Beth Torpey | Jenn Smirniotopoulos | X |  |  |  | X |  |  | Internal meeting with BAS PMO
| 125A | N | N/A | Pending | 2 | OTC | Receipts and Collections | • Create Manual Bill (Invoice) • Create and Apply Receipts • Maintain Unapplied Receipts Dunning Process and Delinquent debt referral | March | 2021-03-10 | 9:30 - 10 AM |  | 2021-03-10 | 0.5 | Mary Beth Torpey | Jenn Smirniotopoulos | X |  |  |  | X |  |  | Internal meeting with BAS PMO
| 36 | Y | N/A | Pending | 2 | PRISM | Award Management | • Associating line items to requisitions • Performing a funds check against the financial system • Validating the vendor against SAM • Adding clauses and sections • Managing warrants • Loading attachments and supporting documents • Sending the award notice to the vendor in FedConnect • Distributing the award to a list of users (internal and external to PRISM) • Creating additional award types (BPA, BPA call, purchase order, contract, delivery/task order) | March | 2021-03-03 | 10 AM - 2 PM |  | 2021-03-10 | 4 | Mary Beth Torpey | Molly Brewer | X | X |  |  | X |  | X | Updated time to reflect West Coast time zones | Y
| 123 | Y | Y | Pending | 2 | OTC | Reporting and Analysis | • Overview of standard receivables reports • Generate Standard Receivables Reports • Review Standard Receivables Reports | March | 2021-03-10 | 1 PM - 3 PM |  | 2021-03-11 | 2 | Mary Beth Torpey | Jenn Smirniotopoulos | X | X |  |  |  |  | X |  | Y
| 125B | Y | Y | Pending | 2 | OTC | Receipts and Collections | • Create Manual Bill (Invoice) • Create and Apply Receipts • Maintain Unapplied Receipts Dunning Process and Delinquent debt referral | March | 2021-03-04 | 1 PM - 3 PM |  | 2021-03-16 | 2 | Mary Beth Torpey | Jenn Smirniotopoulos | X | X |  |  |  |  | X |  | Y
| 10B | N | N/A | Cancelled | 2 | PTR | Journal Reversal (Manual) | • Auto Reversal • Manual-Entry Journal Reversal • Single - Entry Reversal business scenarios |  | 2021-03-04 | 1 PM - 2 PM |  | 2021-03-18 | 1 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  |  | X | Assumes no deep dive required that this can be provide to the communities based on confirmation via email of the required workflow
| 107B | Y | Y | Pending | 3 | Projects | (GINV) Interagency Agreements​: Servicing Agency | Review Policies related to IAA • Enter Agreement without Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | April | 2021-03-18 | 1 PM - 3 PM | 2021-04-19 | Push to April | 2 | Mary Beth Torpey | Jenn Smirniotopoulos |  | X |  | X |  |  | X | General Meeting - more specific IAA's meetings to come in May | Y
| 14 | Y | N/A | Pending | 2 | PTR | Budget Entry/Funds Status Report | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report | March | 2021-03-25 | 10 AM - 12 PM 1 PM - 3 PM |  | 2021-03-25 | 4 | Mary Beth Torpey | Darsh Patel | X | X |  |  |  |  | X |  | Y
| 101 | Y | Y | Pending | 1 | Projects | Project Basics | • Review Project Number and Task Number standardization • Review Project Types and Templates | December | 2020-12-08 | 1 PM - 3 PM |  | N/A | 2 |  |  | X | X | X |  |  |  | X | Updated name of the meeting to Project Basics; maintaing current audience and time/date | Done
| 104 | N | Y | Cancelled | 1 | Projects | Labor Costs and other External Costs interfaced into Oracle Projects | • Identify Type of Cost (Labor + External Cost) interfaced into PA • Source and target for the integration • Data elements • External costs and accounting | November | 2020-11-17 | 1 PM - 3 PM |  | N/A | 2 |  |  | X | X |  | X |  | X |  | Recommendation is to cancel this with the larger audience; as necessary, we will work internally with BAS PMO to address questions | Canceled
| 105 | N | Y | Cancelled | 1 | Projects | Labor Costs and other External Costs interfaced into Oracle Projects | • Identify Type of Cost (Labor + External Cost) interfaced into PA • Source and target for the integration • Data elements • External costs and accounting | December | 2020-12-17 | 1 PM - 3 PM |  | N/A | 2 |  |  | X | X | X |  |  |  | X | Will leverage discussion in Sprint 3; cancelled for Sprint 1 audience | Canceled
| 116 | N | Y | Cancelled | 3 | Projects | Accounting in Projects | • Review of the accounting generated in Projects • Accounting for costs (Burden, allocations) • Accounting for Revenue and Invoices | November | 2020-11-24 | 1 PM - 3 PM |  | N/A | 2 |  |  | X | X |  |  |  | X |  | Recommendation is to cancel this with the larger audience; as necessary, we will work internally with BAS PMO to address questions | Canceled
| 64 |  |  | Pending | 3 | SF PP + Fleet | Acquisition PP + Fleet | Current As-IS Acquisition Process Review System of Record Incorporation Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) Owned vs. Leased Assets Software Assets Work in Progress (CIP) Asset Level User Defined Fields Global User Designed Fields | January | 2021-01-19 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 65 |  |  | Pending | 3 | SF PP + Fleet | Utilization PP + Fleet | Current As-Is Utilization Process Role Review & Requirements Work Flow Required Processes Ongoing Events - Asset Transactions Ongoing Events - User Defined Fields Mapped Ongoing Events Requests - Asset Requests Requests - User Defined Fields (Request / Approve) | January | 2021-01-20 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 66 |  |  | Pending | 3 | SF PP + Fleet | Utilization PP + Fleet | Current As-Is Utilization Process Role Review & Requirements Work Flow Required Processes Ongoing Events - Asset Transactions Ongoing Events - User Defined Fields Mapped Ongoing Events Requests - Asset Requests Requests - User Defined Fields (Request / Approve) | January | 2021-01-21 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 67 |  |  | Pending | 3 | SF PP + Fleet | Finance Treatment PP + Fleet | Current As-Is Business Process Review Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Maintenance Cost Treatment Disposals Treatment Leased Assets Treatment Work in Progress Treatment Software Asset Treatment Bulk Purchase Treatment Useful Lifecycle Salvage Value | January | 2021-01-29 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 68 |  |  | Pending | 3 | SF PP + Fleet | Finance Treatment PP + Fleet | Current As-Is Business Process Review Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Maintenance Cost Treatment Disposals Treatment Leased Assets Treatment Work in Progress Treatment Software Asset Treatment Bulk Purchase Treatment Useful Lifecycle Salvage Value | January | 2021-01-27 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 69 |  |  | Pending | 3 | SF PP + Fleet | Disposals PP + Fleet | Current As-Is Business Process Review Final Event Types - Disposal Type Final Event User Defined Fields Identify any processes which may affect Finance Treatment | January | 2021-01-28 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 70 |  |  | Pending | 3 | SF PP + Fleet | Reporting / Interfaces PP + Fleet | As-Is Reporting Processes As-Is Interfaces & Processed External Reporting Report Needs FAST ALD Disposal | February | 2021-02-02 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X |  | X |  | X |  |  | Y
| 71 |  |  | Pending | 3 | SF PP + Fleet | Acquisition PP + Fleet | Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) | February | 2021-02-03 | 1 PM - 3 PM |  | SPRINT 3 | 4 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 72 |  |  | Pending | 3 | SF PP + Fleet | Utilization PP + Fleet | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | February | 2021-02-04 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | SPRINT 3 | 4 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 73 |  |  | Pending | 3 | SF PP + Fleet | Utilization PP + Fleet | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | February | 2021-02-09 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | SPRINT 3 | 4 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 74 |  |  | Pending | 3 | SF PP + Fleet | Finance Treatment PP + Fleet | Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress | February | 2021-02-10 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | SPRINT 3 | 4 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 75 |  |  | Pending | 3 | SF PP + Fleet | Finance Treatment PP + Fleet | Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress Leased Assets Treatment Work in Progress Treatment Useful Lifecycle Salvage Value | February | 2021-02-11 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | SPRINT 3 | 4 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 76 | Y |  | Pending | 3 | SF PP + Fleet | Disposals PP + Fleet | Final Event Types - Disposal Type Final Event User Defined Fields | February | 2021-02-16 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  | SPRINT 3 | 4 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 77 | Y |  | Pending | 3 | SF PP + Fleet | Reporting / Interfaces PP + Fleet | As-Is Reporting Processes As-Is Interfaces & Processed External Reporting Report Needs Disposal FAST VLD Financial Interfaces HR Interfaces | February | 2021-02-17 | 1 PM - 3 PM |  | SPRINT 3 | 2 | Mary Beth Torpey | Mike Tanner | X | X | X |  |  |  | X |  | Y
| 135 | N | Y | Pending | 2 | INT | GOL/ASAP | Dev/Test Environment Connectivity Commitments Obligations ASAP Authorization ASAP Treasury Draw Grantee Management/SAM Record Approval Workflow | March | 2021-03-09 | TBD |  | TBD | 1 | Jae Lee | Phyllis Keehn | X | [6 empty] | Change to TBD, find out GEMS timeline before we design/build | Y
| 136 | N | Y | Pending | 2 | INT | GMIS/ASAP | Dev/Test Environment Connectivity Commitments Obligations ASAP Authorization ASAP Treasury Draw Grantee Management/SAM Record Approval Workflow | March | 2021-03-11 | TBD |  | TBD | 1 | Jae Lee | Phyllis Keehn | X | [6 empty] | Change to TBD, find out GEMS timeline before we design/build | Y
| 1 | N | N/A | Complete | 1 | PTR | SLA Posting Model Review | • Review SLA Posting Model • Standard USSGL postings for accounting events across EBS modules • Treasury Codes, USSGL Account DR/CR pairs validation | September | N/A | N/A |  |  | 1 |  |  | X |  |  |  |  | X |  | Complete | N
| 2 | N | N/A | Complete | 1 | PTR | PTR Requirements | Review any open requirements | September | N/A | N/A | [5 empty] | X | X |  | X |  | X |  | Via email until additional discussions required | N
| 3 | N | N/A | Complete | 1 | PTR | Ledger Overview | • Overview of the single consolidated DOC Ledger approach • Data Access Control functionality • Operating Units | October | 2020-10-13 | 1 PM - 3 PM |  |  | 2 | John Kim / Rick Murray | Darsh Patel | X | X |  |  |  | X |  |  | Y
| 4 | Y | N/A | Pending | 1 | PTR | Ledger Overview | • Overview of the single consolidated DOC Ledger approach • Data Access Control functionality • Operating Units | December | 2020-12-10 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X |  | Done
| 5 | N | N/A | Complete | 1 | PTR | Plan to Report – BAS ACS Detailed Review | • CBS ACCS to BAS ACS Crosswalk • Sample Segment values • Transaction Accounting String • Program Code to Program Activity mapping | October | 2020-10-22 | 1 PM - 2 PM |  |  | 1 |  |  | X | X |  |  |  | X |  |  | Done
| 6 | Y | N/A | Complete | 1 | PTR | PTR BAS ACS Detailed Review | • CBS ACCS to BAS ACS Crosswalk • Sample Segment values • Transaction Accounting String • Program Code to Program Activity mapping | October | 2020-10-27 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  | X |  | Same content but just ACS101 to establish common understanding | Done
| 7 | Y | N/A | Complete | 1 | PTR | Cross Validation Rules | • Review capabilities • Confirm DOC approach | November | 2020-11-05 | 1 PM - 2 PM |  |  | 1 |  |  | X | X |  |  |  | X |  |  | Done
| 8 | Y | N/A | Pending | 1 | PTR | Cross Validation Rules | • Review capabilities • Demonstrate Cross Validation impact transactional level | December | 2020-12-01 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  | X | X |  | Done
| 11 | N | Y | Cancelled | 3 | PTR | G Invoicing Approach | • G Invoicing Integration approach • Understand known / current G Invoicing plan for PRISM & Oracle | February | 2021-02-23 | 1 PM - 2 PM |  |  | 1 |  |  | X | X |  |  |  | X |  | Discussion overall of the G Invoicing Approach with the users; assumes Phase 1 patches are released. Subject to Change | Y
| 12 | N | Y | Cancelled | 3 | PTR | G Invoicing Approach | • G Invoicing Integration approach • Understand known / current G Invoicing plan for PRISM & Oracle | March | 2021-03-09 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  | X |  | Discussion overall of the G Invoicing Approach with the users; assumes Phase 1 patches are released. Subject to Change | Y
| 15 |  | Y | Pending | 3 | PTR | GTAS/DATA Act Reporting | • GTAS Attributes • DATA Act Configurations • Reporting guidance across Department; bureau submission | April | 2021-04-15 | 1 PM - 3 PM | 2021-04-28 |  | 2 |  |  | X | X |  |  |  | X |  |  | Y
| 16 |  | Y | Pending | 3 | PTR | GTAS/DATA Act Reporting | • GTAS Attributes • DATA Act Configurations • Generating GTAS/DATA Act Reports | June | 2021-06-08 | 10 AM - 12 PM 1 PM - 3 PM | 2021-06-24 |  | 4 |  |  | X | X | X |  |  |  | X |  | Y
| 17 |  |  | Pending | 3 | PTR | Month End Close Process | • Month End Process • Standard PTR Reports | April | 2021-04-20 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  |  |  | X |  |  | Y
| 18 |  |  | Pending | 3 | PTR | Month End Close Process | • Month End Process • Standard PTR Reports | June | 2021-06-10 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X |  | Y
| 19 |  | Y | Pending | 3 | PTR | Year End Close Process | • Year End Closing Definitions • Standard Year End Close Process | April | 2021-04-22 | 1 PM - 3 PM | 2021-05-12 |  | 2 |  |  | X | X |  |  |  | X |  |  | Y
| 20 |  | Y | Pending | 3 | PTR | Year End Close Process | • Year End Closing Definitions • Standard Year End Close Process | June | 2021-06-15 | 1 PM - 3 PM | 2021-06-30 |  | 2 |  |  | X | X | X |  |  |  | X |  | Y
| 21 | N | N/A | Complete | 1 | PRISM | PRISM Requirements | Review any open requirements | September | N/A | N/A | [5 empty] | X | X |  | X |  |  |  | Via email until additional discussions required | N
| 22 | N | N/A | Complete | 1 | PRISM | Advanced Acquisition Planning Demo | • Building collaborative acquisition workspaces based on pre-defined templates • Adding, revising, and searching internal notes • Establishing and managing integrated project teams • Tracking acquisition-related data • Developing vendor deliverable schedules • Establishing acquisition milestone schedules • Developing acquisition packages using Microsoft Word and PDF templates • Generating an electronic contract file folder structure • Budget planning for year-over-year commitments and obligations | October | 2020-10-08 | 9 AM - 11 AM |  |  | 2 | Mary Beth Torpey | Randy Platter | X | X |  | X |  |  | X |  | Y
| 23 | N | N/A | Complete | 1 | PRISM | Advanced Acquisition Planning Workshop | • Determine the following information: - Templates based on acquisition type - Note types - Data elements to capture - Integrated procurement teams | October | 2020-10-13 | 1 PM - 5 PM |  |  | 4 | Mary Beth Torpey | Randy Platter | X | X |  | X |  |  | X |  | Y
| 24 | N | N/A | Complete | 1 | PRISM | Advanced Acquisition Planning Workshop | • Determine the following information: - Vendor deliverable schedules - Cost tracking and objective tabs - Milestones | October | 2020-10-15 | 9 AM - 5 PM |  |  | 8 | Jae Lee / Rick Murray | Randy Platter | X | X |  | X |  |  | X |  | Y
| 25 | N | N/A | Complete | 1 | PRISM | Advanced Acquisition Planning Workshop | • Determine the following information: - Word templates - Folder structures - Document categories | October | 2020-10-21 | 9 AM - 1 PM |  |  | 8 |  |  | X | X |  | X |  |  | X |  | Done
| 26 | Y | N/A | Pending | 1 | PRISM | Advanced Acquisition Planning | • Building collaborative acquisition workspaces based on pre-defined templates • Adding, revising, and searching internal notes • Establishing and managing integrated project teams • Tracking acquisition-related data • Developing vendor deliverable schedules • Establishing acquisition milestone schedules • Developing acquisition packages using Microsoft Word and PDF templates • Generating an electronic contract file folder structure • Budget planning for year-over-year commitments and obligations | December | 2020-12-08 | 9 AM - 1 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 27 | Y | N/A | Complete | 1 | PRISM | Requisition Management Demo | • Structuring line items • Routing to pre-established routing lists • Loading attachments and supporting documents • Sending requisitions to the Unison Marketplace | October | 2020-10-28 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | [6 empty] | Done
| 28 | Y | N/A | Complete | 1 | PRISM | Requisition Management Workshop | • Determine the following information: - Standard requisition numbering masks - Route roles - Additional information to track outside of COTS fields | November | 2020-11-04 | 9 AM - 1 PM |  |  | 4 |  |  | X | X |  | X |  |  | X |  | Done
| 29 | Y | N/A | Pending | 1 | PRISM | Requisition Management | • Structuring line items • Performing a funds check • Routing to pre-established routing lists • Loading attachments and supporting documents • Sending requisitions to the Unison Marketplace | December | 2020-12-10 | 9 AM - 12 PM |  |  | 3 |  |  | X | X | X |  |  |  | X |  | Done
| 37 |  |  | Pending | 3 | PRISM | Post Award Management and Closeout Demo | • Processing funded and unfunded modifications • Sending and receiving files and messages through the FedConnect vendor portal • Viewing select financial data in PRISM • Loading and completing a closeout checklist • Closing awards in PRISM and FPDS | April | 2021-04-06 | 10 AM - 12 PM |  |  | 2 |  |  | X | X |  | X |  | X
| 38 |  |  | Pending | 3 | PRISM | Post Award Management and Closeout Workshop | • Determine the following information: - Closeout checklists - Additional post-award functionality | April | 2021-04-14 | 10 AM - 12 PM |  |  | 2 |  |  | X | X |  | X |  | X
| 39 |  |  | Pending | 3 | PRISM | Post Award Management and Closeout | • Processing funded and unfunded modifications • Sending and receiving files and messages through the FedConnect vendor portal • Viewing select financial data in PRISM • Loading and completing a closeout checklist • Closing awards in PRISM and FPDS | June | 2021-06-23 | 10 AM - 12 PM |  |  | 2 |  |  | X | X | X |  |  |  | X
| 40 |  |  | Pending | 3 | PRISM | Security Group Workshop | • Establish security groups and privileges | May | 2021-05-19 | 1 PM - 5 PM |  |  | 4 |  |  | X | X |  | X |  | X
| 41 |  |  | Pending | 3 | PRISM | Security Group Workshop | • Establish security groups and privileges | May | 2021-05-26 | 1 PM - 5 PM |  |  | 4 |  |  | X | X |  | X |  | X
| 42 |  |  | Pending | 3 | PRISM | Reporting | • Review reporting requirements and PRISM capabilities | June | 2021-06-02 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X
| 43 |  |  | Pending | 3 | PRISM | Reporting | • Review reporting requirements and PRISM capabilities | June | 2021-06-16 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X
|  |  |  | Pending | 3 | PRISM and EBS | PRISM - EBS: Requisitions | • Review PRISM-EBS interface touchpoints for requisitions | April | 2021-04-27 | 10 AM - 12 PM |  |  | 2 |  |  | X | X |  |  |  | X
|  |  |  | Pending | 3 | PRISM and EBS | PRISM - EBS: Awards | • Review PRISM-EBS interface touchpoints for awards | May | 2021-05-04 | 10 AM - 12 PM |  |  | 2 |  |  | X | X |  |  |  | X
| 42 |  |  | Pending | 4 | PRISM or PTP | (GINV) G Invoicing Approach - Requesting Agency | Review PRISM Capabilities related to PRISM business process flows | April | 2021-04-13 | 11 AM - 12 PM | 2021-05-17 | 1 PM - 3 PM | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 43 |  |  | Pending | 4 | PRISM or PTP | (GINV) G Invoicing Approach - Requesting Agency | Review PRISM Capabilities related to PRISM business process flows | May | 2021-05-20 | 11 AM - 12 PM | 2021-05-17 | 1 PM - 3 PM | 2 |  |  | X | X | X |  |  |  | X |  | Y
| 44 |  |  |  | 1 | SF Real Property | Review SF Open Requirements | • Review questions on requirements | September | N/A | N/A | [12 empty] | Via email until additional discussions required | N
| 45 | N | N/A | Complete | 1 | SF Real Property | Review SF RP Approach | Review Upcoming Meeting Schedule & Flow | September | 2020-09-17 | 3 PM - 4 PM |  |  | 1 | Mary Beth Torpey | Danielle Lyon | X |  |  |  | X | X |  |  | N
| 46 | N | N/A | Complete | 1 | SF Real Property | Review SF RP Approach | Review Upcoming Meeting Schedule & Flow | September | 2020-09-22 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Danielle Lyon | X | X |  | X |  | X |  |  | N
| 47 | N | N/A | Complete | 1 | SF Real Property | Common Solution Kickoff | Review CS Approach Review SF Navigation if necessary | September | 2020-09-30 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Danielle Lyon | X | X | X |  |  | X |  |  | Y
| 48 | N | N/A | Complete | 1 | SF Real Property | Acquisition (RP) | Current As-Is Acquisition Process System of Record Incorporation Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) | October | 2020-10-06 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Danielle Lyon | X | X |  | X |  | X |  |  | Y
| 49 | N | N/A | Complete | 1 | SF Real Property | Utilization (RP) | Current As-Is Utilization Process Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | October | 2020-10-07 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Danielle Lyon | X | X |  | X |  | X |  |  | Y
| 50 | N | N/A | Complete | 1 | SF Real Property | Utilization (RP) | Current As-Is Utilization Process Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | October | 2020-10-08 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Danielle Lyon | X | X |  | X |  | X |  |  | Y
| 51 | N | N/A | Complete | 1 | SF Real Property | Finance Treatment (RP) | Current As-Is Business Process Review Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress | October | 2020-10-13 | 1 PM - 3 PM |  |  | 2 | Mike Tanner / MBT | Danielle Lyon | X | X |  | X |  | X |  |  | Y
| 52 | N | N/A | Complete | 1 | SF Real Property | Finance Treatment (RP) | Current As-Is Business Process Review Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress Leased Assets Treatment Work in Progress Treatment Useful Lifecycle Salvage Value | October | 2020-10-14 | 1 PM - 3 PM |  |  | 2 | Mike Tanner / MBT | Danielle Lyon | X | X |  | X |  | X |  |  | Y
| 53 | N | N/A | Complete | 1 | SF Real Property | Disposals (RP) | Current As-Is Business Process Review Final Event Types - Disposal Type Final Event User Defined Fields | October | 2020-10-20 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X |  |  | Done
| 54 | N | N/A | Complete | 1 | SF Real Property | Reporting / Interfaces (RP) | Current As-Is Business Process Review Final Event Types - Disposal Type Final Event User Defined Fields | November | 2020-10-21 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X |  |  | Done
| 55 | N | N/A | Complete | 1 | SF Real Property | Acquisition (RP) | Initial Event Types (Acquisition Types) Initial Event User Defined Fields (Additional Fields) Acquisition Entry (Manual / Interface) | December | 2020-10-22 | 10 AM - 11:30 AM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 56 | Y | Y | Cancelled | 1 | SF Real Property | Utilization (RP) | Space Planning & Space Details Maintenance Agreements (Commercial / Occupancy Agreements / Service Agreements) Lease Billing (Commercial / ROW) Organization Types & Contacts Parking & Occupancy Property Documents Surveys & Assessments Projects Associated to Property Operating Costs Performance Measures | December | 2020-10-27 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 57 | Y | Y | Complete | 1 | SF Real Property | SF Real Property Utilization and Disposals | • Space Planning & Space Details • Maintenance • Agreements (Commercial / Occupancy Agreements / Service Agreements) • Lease Billing (Commercial / ROW) • Organization Types & Contacts • Parking & Occupancy • Property Documents • Surveys & Assessments • Projects Associated to Property • Operating Costs • Performance Measures • Final Event Types - Disposal Type • Final Event User Defined Fields | December | 2020-10-28 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X |  | Done
| 59 | Y | Y | Cancelled | 1 | SF Real Property | Finance Treatment (RP) | Capitalization Process Decapitalization Process Journal Entry Rules & Template Templates Adjustments Decapitalization Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress Leased Assets Treatment Work in Progress Treatment Useful Lifecycle Salvage Value | January | 2020-11-03 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 60 | Y | Y | Cancelled | 1 | SF Real Property | Disposals (RP) | Final Event Types - Disposal Type Final Event User Defined Fields | January | 2020-11-04 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 78 |  |  |  | 1 | PTP | AP Requirements Review | • Review any open requirements required for Common Solution (Receipts, Grants, AP reporting) | October | N/A | N/A | [5 empty] | X | X |  |  |  | X |  | Via email until additional discussions required | N
| 79 |  |  | Pending | 3 | PTP | SAM/ Vendor Management | • Overview of Vendor Maintenance • SAM Interface Data Flow and Refresh • SAM/Non-SAM Vendors & Management/Maintenance • FOMF/APSI | May | 2021-05-03 | 1 PM - 2 PM | 2021-05-11 |  | 1 |  |  | X | X | [5 empty] | vendor management added SAM to the discussion | Y
| 81 | Y | N/A | Pending | 1 | PTP | AP Invoices | • EBS AP Invoice Overview • Approval Hierarchies • Overview of Invoice Entry/Approval Hierarchies/Holds/Adjustment scenarios • Discuss any unique/current business scenarios for Invoice Holds & Adjustments | November | 2020-11-16 | 1 PM - 3 PM | 2021-06-08 |  | 2 |  |  | X | X |  |  |  | X |  |  | Done
| 82 | Y | N/A | Pending | 1 | PTP | AP Invoices | • EBS AP Invoice and Grants Demo • Overview of Invoice Entry/Approval Hierarchies/Holds/Adjustment scenarios • Discuss any unique/current business scenarios for Invoice Holds & Adjustments | December | 2020-12-14 | 10 AM - 12 PM 1 PM - 3 PM | 2021-05-18 |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 83 |  |  | Pending | 3 | PTP | P-Card (SmartPay3) | • P-Card <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the P-Card process/etc. • Discuss unique scenarios for P-Card transactions and Reconciliation processes | April | 2021-04-05 | 1 PM - 2 PM | 2021-06-08 |  | 1 |  |  | X | X | [6 empty] | Y
| 84 |  |  | Pending | 3 | PTP | Travel (MLINQ/CWT/E2) | • CWT/E2/MLINQ <> EBS Interface Data Flow, Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the Travel process/etc. • Authorizations & Vouchers <> Obligations & Invoices • Discussion of unique travel transactions within the DOC | April | 2021-04-11 | 1 PM - 2 PM | 2021-05-18 |  | 1 |  |  | X | X | [6 empty] | Y
| 87 |  |  | Pending | 3 | PTP | T-Card (SmartPay3) | • T-Card <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the T-Card process/etc. • Discuss unique scenarios for T-Card transactions and Reconciliation processes | May | 2021-05-17 | 1 PM - 3 PM | 2021-05-27 |  | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 88 |  |  | Pending | 3 | PTP | F-Card (SmartPay3) | • F-Card <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the F-Card process/etc. • Discuss unique scenarios for F-Card transactions and Reconciliation processes | June | 2021-06-07 | 10 AM - 12 PM 1 PM - 3 PM | 2021-06-01 |  | 4 |  |  | X | X | X | [5 empty] | Y
| 89 |  |  | Pending | 4 | PTP | Vendor e-Invoicing | • Scope clarification for E-Invoicing platform (pending) • Basic functionality of E-Invoicing Platform vs. Requirements • Discovery more than a Functional conversation | April | 2021-04-25 | 1 PM - 3 PM | 2021-06-28 |  | 2 |  |  | X | X |  | X |  | X |  | Update to Sprint 4 to accomodate solution discussions, LMO 2.23.21 | Y
| 90 |  |  | Pending | 4 | PTP | Vendor e-Invoicing | • Overview of capabilities / approach for Vendor E-Portal Requirements • E-Invoicing platform <> EBS Integration • Invoicing process via E-Invoicing platform | June | 2021-06-21 | 1 PM - 3 PM | 2021-07-01 |  | 2 |  |  | X | X | X |  |  |  |  | Update to Sprint 4 to accomodate solution discussions, LMO 2.23.21 | Y
| 91 |  |  | Pending | 3 | PTP | Payroll | • Overview of integration to Payroll <> EBS, Data flow • Discuss current DOC requirements on Payroll practices | April | 2021-04-05 | 1 PM - 3 PM | 2021-06-17 |  | 2 |  |  | X | X | X | [5 empty] | Y
| 93 |  |  |  | 1 | Projects | Project Costing Requirements | Review any open requirements | September | N/A | N/A | [5 empty] | X | X |  | X |  | X |  | Via email until additional discussions required | Y
| 94 |  |  |  | 1 | Projects | Project Billing Requirements | Review any open requirements | September | N/A | N/A | [5 empty] | X | X |  | X |  | X |  | Via email until additional discussions required | Y
| 95 | N | Y | Cancelled | 1 | Projects | Cost Allocation Part I | • Discuss policy • Present and Discuss Costs allocated Source, Target and Conditions (using DOC cost allocation methodology) • Present and Discuss Cost Allocation Methods: calculation, data elements (ex: specific OC) • Identify Scenarios of Cost Allocation standardization • Discuss Accounting | October | 2020-10-27 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X |  | Cancelled for larger audience - need to create session with smaller group with BAS PMO (including initial questions via email as appropriate); MBT to coordinate | Canceled
| 97 | Y | N/A | Pending | 1 | Projects | Cost Allocation | •Present and Discuss Costs allocated Source, Target and Conditions (using DOC cost allocation methodology) • Present and Discuss Cost Allocation Methods: calculation, data elements (ex: specific OC) • Identify Scenarios of Cost Allocation standardization • Discuss Accounting | December | 2020-12-15 | 10 AM - 12 PM 1 PM - 3 PM |  |  | 4 |  |  | X | X | X |  |  |  | X | Dependent upon the outcomes of Cost Allocation Internal discussions; we would show the configurations from the matrix to the system impact | Done
| 98 |  |  | Pending | 3 | Projects | Reporting and Analysis (Cost and Expenditures) | Review Standard Oracle Reports related to cost and expenditures | June | 2021-04-19 | 1 PM - 3 PM | 2021-06-30 | Push to June | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 99 |  |  | Pending | 4 | Projects | (GINV) Reporting and Analysis (Reimbursables and IAA's) | Review Standard Oracle Reports related to Reimbursables and IAA'S | August | 2021-06-15 | 1 PM - 3 PM | 2021-08-02 | Push to late summer due to patch releases | 2 |  |  | X | X | X |  |  |  | X |  | Y
| 100 | N | N/A | Complete | 1 | Projects | Data Standardization | • Understand and Discuss DOC documentation on data standardization needs • Collaborate with DOC stakeholders on communicating policy | October | 2020-10-08 | 1 PM - 3 PM |  |  | 2 | Tracey Carpenter | Jenn Smirniotopoulos | X | X |  | X |  | X |  |  | Y
| 103 | Y | N/A | Pending | 1 | Projects | Object Classes | • Review Standard Object Classes in Oracle Projects • Review DOC specific Object Classes and Accounting | December | 2020-12-10 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X |  | Done
| 108 |  |  | Pending | 3 | Projects | (GINV) Interagency Agreements​: Servicing Agency Pt. 2 | • Enter Agreement without Advance (Federal Customer)​; • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance, • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | May | 2021-04-15 | 10 AM - 12 PM or 1 PM - 3 PM | 2021-05-03 | Monday or Wednesday; follow-up after 107B - early May | 2 |  |  | X | X | X |  |  |  | X |  | Y
| 109A |  |  | Pending | 3 | Projects | (GINV) Create Funding | • Identify scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting | May | 2021-05-11 | 1 PM - 3 PM | 2021-05-10 | BAS PMO Review; Adjusted for PDK schedule with client | 0.5 |  |  | X | X |  | X |  | X |  |  | Y
| 109B |  |  | Pending | 3 | Projects | (GINV) Create Funding | • Identify scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting | May | 2021-05-11 | 1 PM - 3 PM | 2021-05-17 | Leave in Sprint 3 | 2 |  |  |  | X |  | X |  | X |  |  | Y
| 110A |  |  | Pending | 4 | Projects | (GINV) Generate Billing and Revenue (Non-advance) | • Review scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting | July | 2021-06-10 | 10 AM - 12 PM OR 1 PM - 3 PM | 2021-07-26 | BAS PMO Review | 1 |  |  | X | X | X |  |  |  | X | Talk with PDK re: game plan and determine who should be included (i.e., OTC SME) | Y
| 110B |  |  | Pending | 4 | Projects | (GINV) Generate Billing and Revenue (Non-advance) | • Review scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting | August | 2021-06-10 | 10 AM - 12 PM OR 1 PM - 3 PM | 2021-07-28 | Push to Sprint 4 | 2 |  |  | X | X | X |  |  |  | X | Talk with PDK re: game plan and determine who should be included (i.e., OTC SME) | Y
| 115 |  |  | Pending | 4 | Projects | (GINV) Generate Billing and Revenue (Advance) | DOC Policy related to: • Track Task Orders Against Agreements​ • Record Advances against Incoming IAAs​ • Track and Report Liquidation of Advances | August | 2021-05-18 | 1 PM - 3 PM | 2021-08-04 | BAS PMO Review | 1 |  |  | X | X |  | X |  | X |  | Talk with PDK re: game plan and determine who should be included (i.e., OTC SME) | Y
| 115 |  |  | Pending | 4 | Projects | (GINV) Generate Billing and Revenue (Advance) | DOC Policy related to: • Track Task Orders Against Agreements​ • Record Advances against Incoming IAAs​ • Track and Report Liquidation of Advances | August | 2021-05-18 | 1 PM - 3 PM | 2021-08-09 | Push to Sprint 4 | 2 |  |  | X | X |  | X |  | X |  | Talk with PDK re: game plan and determine who should be included (i.e., OTC SME) | Y
| 92 |  |  | Pending | 3 | PTP | Payroll & Transactions | • Overview of integration to Payroll/Travel modules within Oracle EBS • Discuss current DOC requirements on Payroll practices | June | 2021-06-17 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X |  | Y
| 117 |  |  |  | 1 | OTC | AR Requirements | Review any open requirements | September | N/A | N/A | [5 empty] | X | X |  | X |  | X |  | Via email until additional discussions required | N
| 118 | N | N/A | Complete | 1 | OTC | Customers | • Customer Creation maintenance and sources of customers • Customer Advances • Customer Holds • Confirm reporting requirements from COTS | October | 2020-10-13 | 1 PM - 3 PM |  |  | 2 | Jae Lee | Jenn Smirniotopoulos | X | X |  | X |  | X |  |  | Y
| 119 | N | N/A | Complete | 1 | OTC | Policy Meeting: Reimbursable Agreements | • Understand and discuss current DOC policies and practices on reimbursable agreements and adjustments to Project transactions and credit memo creation in AR | October | 2020-10-19 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 120 | Y | N/A | Complete | 1 | OTC | Direct Invoicing / Invoice Interface | • Invoice Creation (Manual /invoice interface) • External systems interfacing to AR directly • Customer Holds • Confirm reporting requirements from COTS | October | 2020-10-26 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X |  |  | Done
| 128 |  |  | Pending | 4 | Project/OTC | Federal Interfaces (GINV G-invoicing, IPAC integration and pay.gov) | • Provide overview of key federal interfaces • Discuss current DOC business processes (CIR, pay.gov, etc.) | August | 2021-05-03 | 1 PM - 3 PM | 2021-08-04 | Push to end of Sprint 3 | 2 |  |  | X |  |  | X |  |  |  |  | Y
[5 empty] | 3 |  | Discovery: Federal Interfaces (GINV G-invoicing, IPAC integration and pay.gov) | • Understand overview of key federal interfaces • Discuss current DOC business processes (CIR, pay.gov, etc.) | June | 2021-06-21 |  | 2021-06-21
| 129 |  |  | Pending | 4 | Project/OTC | Federal Interfaces (GINV G-invoicing, IPAC integration and pay.gov) | • Provide overview of key federal interfaces • Discuss current DOC business processes (CIR, pay.gov, etc.) | August | 2021-06-02 | 1 PM - 3 PM | 2021-08-11 | Push to end of Sprint 3 | 2 |  |  |  | X | X |  |  | X | X |  | Y
| 121 | Y | N/A | Pending | 1 | OTC | Billing | • Multi fund AR accounting • Other Accounting requirements • AR Auto accounting • Revenue Recognition rules in AR • Credit Memo approvals | November | 2020-11-10 | 1 PM - 3 PM |  |  | 3 |  |  | X | X | X |  |  |  | X |  | Done
| 130A |  |  | Pending | 4 | OTC | GINV IAA Billing/Collections | Review GINV Billing/Collections process for Servicing Agency | July | 2021-04-08 | 1 PM - 3 PM | 2021-07-19 | BAS PMO Review | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 130B |  |  | Pending | 4 | OTC | GINV IAA Billing/Collections | Review GINV Billing/Collections process for Servicing Agency | July | 2021-04-08 | 1 PM - 3 PM | 2021-07-21 | Push to Sprint 4 | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 131 |  |  | Pending | 3 | OTC | IPAC Processing (Non-IAA buy/sell) | Review DOC IPAC transactions not related to buy/sell activity | April | TBD | 1 PM - 2 PM | 2021-04-07 | PDK requested only one hour and it'll be an informal conversation | 1 |  |  | X | X | X |  |  |  | X | FYSA - Information gathering session (informal conversation) | Y
| 132 |  |  | Pending | 3 | OTC | Consolidated Billing | Review DOC standards / approach / policies related to Consolidation of Invoices | April | 2021-04-15 | 10 AM - 12 PM 1 PM - 3 PM |  |  | 1 |  |  | X | X |  | X |  | X |  |  | Y
| 138 |  |  | Pending | 3 | INT | HFM | Financial Statement Data Extract Requirement BAS Financials/EDW Considerations | June | 2021-06-08 | 10 AM - 11 AM |  |  | 1 |  |  | X | X | [6 empty] | Y
| 139 |  |  | Pending | 3 | INT | NFC | Master Employee Record NFC Payroll Payroll Estimate USCG Payroll Decennial Payroll | April | 2021-04-29 | 10 AM - 11 AM |  |  | 1 |  |  | X | X | [6 empty] | Y
| 140 |  |  | Pending | 3 | INT | Pay.gov, NOAA | Collections Information Repository (CIR) Seafood Acceptance System | May | 2021-05-11 | 10 AM - 11 AM |  |  | 1 |  |  | X | X | [6 empty] | Y
| 141 |  |  | Pending | 3 | INT | Pay.gov, NIST | Standard Reference Data (SRD) Baldridge Salesforce Calibration Payment Misc. Payment | May | 2021-05-11 | 1 PM - 2 PM |  |  | 1 |  |  | X | X | [6 empty] | Y
| 142 |  |  | Pending | 3 | INT | Pay.gov, Census | Data Sales Interface (DSI) | May | 2021-05-13 | 10 AM - 11 AM |  |  | 1 |  |  | X | X | [6 empty] | Y
| 145 |  |  | Pending | 3 | INT | MoveLINQ | Dev/Test Environment Connectivity Relocation Authorizations Relocation Vouchers Accounting Strings Employee Record | June | 2021-06-08 | 10 AM - 11 AM |  |  | 1 |  |  | X | X | [6 empty] | Y
| 158 | Y | N/A | Pending | 1 | INT | PRISM/EBS | Dev/Test Environment Connectivity Commitments Obligations Vendor Sync Fund Check | November | 2020-11-17 | 10 AM - 11 AM |  |  | 1 |  |  | X | [7 empty] | Done
| 159 | Y | N/A | Pending | 1 | INT | Sunflower/EBS | Dev/Test Environment Connectivity Mass Asset Addition Sunflower Financial to EBS | November | 2020-11-19 | 10 AM - 11 AM |  |  | 1 |  |  | X | [7 empty] | Done
| 160 | N | N/A | Complete | 1 | All | Review CS Kickoff | Review CS Kickoff Materials | September | 2020-09-23 | 11 AM - 12 PM |  |  | 1 | Mary Beth Torpey | Mary Beth Torpey | X |  |  |  |  | X |  |  | N
| 111A |  |  | Pending | 3 | Projects | (GINV) Interagency Agreements (Advance): Servicing Agency | • Enter Agreement with Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification current business cases for IAA With-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Accounting • Capturing Performance Period and Budget Period for Incoming IAAs | June |  |  | 2021-06-14 |  | 2 |  |  | x
| 111B |  |  | Pending | 3 | Projects | (GINV) Interagency Agreements (Advance): Servicing Agency | • Enter Agreement with Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification current business cases for IAA With-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Accounting • Capturing Performance Period and Budget Period for Incoming IAAs | June | 2021-06-24 | 1 PM - 3 PM | 2021-06-21 |  | 2 |  |  | X | X |  | X |  | X |  |  | Y
| 112 |  |  | Cancel | 4 | Projects | (GINV) Creating Interagency Agreements (Advance) | • Enter Agreement with Advance (Federal Customer)​ • Agreement fields (Mapping..) • Review current business cases for IAA With-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Accounting • Capturing Performance Period and Budget Period for Incoming IAAs | July | 2021-07-15 | 10 AM - 12 PM 1 PM - 3 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Y
| 113 |  |  | Cancel | 4 | Projects | Create Funding and Generate Billing and Revenue (With Advance) | • Identify scenarios of Funding Reimbursable IAA with Advance • Recognize Revenue and Billing : Billing method and process • Billing and Revenue: Accounting • Recording ACR​ | July | 2021-07-29 | 1 PM - 3 PM |  |  | 2 |  |  | X | X |  | X |  | X |  |  | Y
+ | 114 |  |  | CANCEL | 4 | Projects | Create Funding and Generate Billing and Revenue (With Advance) | • Review scenarios of Funding Reimbursable IAA with Advance • Recognize Revenue and Billing : Billing method and process • Billing and Revenue: Accounting • Recording ACR​ | Aug | 2021-08-12 | 10 AM - 12 PM 1 PM - 3 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Y
| 161 | N | N/A | Complete | 1 | All | Common Solution Kickoff (1) | Review CS Approach Review SF Navigation if necessary Focus is Acquisition / Financials | October | 2020-10-01 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Mary Beth Torpey | X | X | X |  |  | X |  |  | Y
| 162 | N | N/A | Complete | 1 | All | Common Solution Kickoff (2) | Review CS Approach Review SF Navigation if necessary Focus is Acquisition / Financials | October | 2020-10-07 | 10 AM - 12 PM 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Mary Beth Torpey | X | X | X |  |  | X |  |  | Y
| 102A | N | Y | Cancelled | 1 | Projects | Object Classes | • Standard Object Classes in Oracle Projects • DOC specific Object Classes and Accounting | October | 2020-10-15 | 1 PM - 3 PM |  |  | 2 | Tracey Carpenter | Jenn Smirniotopoulos | X | X |  | X |  | X |  | Cancelled for larger audience ; working internally via email for answers | Y
| 58A | Y | Y | Cancelled | 1 | SF Real Property | Finance Treatment (RP) | Acquisition Financial Treatment Operating Cost Treatment Maintenance Cost Treatment Project Cost Treatment Disposals Treatment Work in Progress | January | 2020-10-29 | 10:00 AM - 12:00 PM; 1:00 PM - 3:00 PM |  |  | 4 |  |  | X | X | X |  |  |  | X |  | Done
| 61A | Y | N/A | Complete | 1 | SF Real Property | Reporting / Interfaces (RP) | As-Is Reporting Processes As-Is Interfaces & Processed External Reporting Report Needs Disposal FRPP ROW | February | 2020-11-05 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X |  |  |  | X |  | Done
| 133 |  |  | Pending | 3 | OTC | Consolidated Billing | • Consolidation of Invoices | June | 2021-06-02 | 1 PM - 3 PM |  |  | 2 |  |  | X | X | X | [5 empty] | Y
| 80A | N | Y | Complete | 1 | PTP | Vendor e-Invoicing | • Overview of capabilities / approach for Vendor E-Portal Requirements • Provide capabilities / approach for Vendor E-Portal Requirements | October | 2020-10-15 | 1 PM - 3 PM |  |  | 2 | Mary Beth Torpey | Loda Opot | X | X |  |  |  | X |  | Meeting only with Karen to understand IPP better from a Functional Design perspective; Change audience (cancelled for larger audience); already scheduled by MBT | Y
| 146 |  |  |  | TBD | INT | PTP Other: NOAA Specific | OPCS Express Small Package System SF270 Invoice Processing GSA Motor Pool Telecom Charges other NOAA PTP interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific PTP focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 147 |  |  |  | TBD | INT | OTC Other: NOAA Specific | NDW extract applications other NOAA OTC interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific OTC focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 148 |  |  |  | TBD | INT | PTR Other: NOAA Specific | other NOAA PTR interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific PTR focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 149 |  |  |  | TBD | INT | NOAA Specific Other | All other interfaces for BAS consideration | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [6 empty] | Y
| 150 |  |  |  | TBD | INT | PTP Other: NIST Specific | American Bankers Association Facilities PO Government Bill of Landing other NIST PTP interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific PTP focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 151 |  |  |  | TBD | INT | OTC Other: NIST Specific | ITA Safe Harbor ITA eMenu OS WCF unbilled collections other NIST OTC interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific OTC focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 152 |  |  |  | TBD | INT | PTR Other: NIST Specific | Administrative Services Division Boulder Plant charges Cryptographic module validation program Department of State interface ITA centralized services Plant Gaithersburg Washington interagency telecommunication services other NIST PTR interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific PTR focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 153 |  |  |  | TBD | INT | NIST Specific Other | Maximo ANTS property All other interfaces for BAS consideration | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [6 empty] | Y
| 154 |  |  |  | TBD | INT | PTP Other: Census Specific | Cost and Response Management Network (CARMIN) Census Printing Management System (CPMS) Express Small Package System (ESPS) Education & Training Management System (ETMIS) IT Business Plan (ITBP)/CAT Postal Transportation Apps ( Carpool, Parking & Subsidy) Other Census PTP interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific PTP focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 155 |  |  |  | TBD | INT | OTC Other: Census Specific | Jeffersonville Time and Attendance System (JTAS) Jeffersonville Activity Reporting System (JARS) Cost Activity Reporting System (CARS) Overtime Authorization Request System (OAR+) T&A Validation Other Census OTC interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific OTC focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 156 |  |  |  | TBD | INT | PTR Other: Census Specific | Consolidated Budget Reporting and Analysis (COBRA) Internal Cost Distribution System (ICDS) Other Census PTR interfaces | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [5 empty] | Initial list of bureau specific interfaces to be discussed during specific PTR focus area sessions for requirement gathering/validation. If it's officially tied to the business process then schedule this as a follow up session to go over technical details. | Y
| 157 |  |  |  | TBD | INT | Census Specific Other | ATRAK CAMPIN Hazardous Materials Tracking (HMT) James Bond Identification (JBOND) PEARS PTCS Safety Monitor Reporting System (SMRS) Unified Tracking System (UTS) All other interfaces for BAS consideration | As needed | TBD | TBD |  |  | 1 |  |  | X | X | [6 empty] | Y
| 158 |  |  |  | 3 | OTC | Customer Refunds | Overview of Functionality Configuration Review Refunds process | May | TBD | 1PM-3PM |  |  | 2 |  |  |  | X |  |  |  | X
| 159 |  |  |  | 3 | OTC | Receipt Remittance | Overview of Functionality Configuration Review Receipt entry Remittance batch creation Reports | April | TBD | 1PM-3PM |  |  | 2 |  |  |  | X |  |  |  | X
| 160 |  |  |  | 3 | OTC | Deposits | Overview of Functionality Configuration Review Deposit Transactions Aplication of Receipts to Deposits Application of Deposit to Invoice Adjustment of Deposits Commitment Report | April | TBD | 1PM-3PM |  |  | 2 |  |  |  | X |  |  |  | X
161
[7 empty] | DNP Interface | • DNP Data flow to Treasury; EBS; PAM • Impact of Data flow between interfaced platforms and BAS | June | 2021-06-24 | 10 AM - 12PM | 2021-06-24 |  | 2 |  |  | X | X
[7 empty] | PRISM to EBS Integration (Part 1) | • Overview of the data flow from PRISM to EBS along PTP workstream • Impact of Data flow between interfaced platforms and BAS | April | 2021-04-27 | 1 PM - 4 PM | 2021-04-27 |  | 2 |  |  | X | X
[7 empty] | PRISM to EBS Integration (Part 2) | • Overview of the data flow from PRISM to EBS along PTP workstream • Impact of Data flow between interfaced platforms and BAS | April | 2021-04-29 | 1 PM - 4 PM | 2021-04-29 |  | 3 |  |  | X | X
[7 empty] | PAM/SPS | • PAM/SPS <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the PAM/SPS process/etc. • Overview of CTA (Classification Transactions + Accountability Process) and monthly accounting activity reports to Treasury | May |  | 1 PM - 3 PM | 2021-05-25 |  | 3 |  |  | X | X
[7 empty] | Receipts | • Review Receipt functionality in EBS | May |  | 11 AM - 12 PM | 2021-05-03 |  | 1 |  |  | X | X |  |  |  | X
[7 empty] | Credit/Debit Memos/Refund Business Process | • Credit/Debit memo functionality in EBS • Bulk file of negative invoices (i.e. credit memos) • Refund business process | April |  | 1 PM - 3 PM | 2021-04-15 |  | 1 |  |  | X | X |  |  |  | X
[7 empty] | CARS | • CARS enrollment |  |  | 1 PM - 2 PM | 2021-06-11 |  | 1 |  |  | X | X |  |  |  | X
[7 empty] | CTA | • Overview of CTA (Classification Transactions + Accountability Process) and monthly accounting activity reports to Treasury |  |  | 1 PM - 2 PM | 2021-06-18 |  | 1 |  |  | X | X |  |  |  | X
| 20 |  |  | Pending | 3 | PTR | CARS and 224 Reconciliation Reports | • CARS Reporting • 224 Reconciliation Reports | May | 2021-05-20 | 1 PM - 4 PM |  | Added session per BAS PMO feedback | 2 |  |  | X | X | X |  |  |  | X |  | Y
Note on K18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RESCHEDULE
Note on N18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RESCHEDULE
Note on N20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RESCHEDULE
Note on H60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Hanayen, Rafaat [i360Technologies Inc] @Smirniotopoulos, Jennifer Does this need a session with the full CS in month 3? Reply: Raf wanted to do this session in November to give some buffer time to understand the implication(s) of g-invoicing on revenue and other aspects (after the first set of patches in October).
Note on H111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm approach for Sprint 4 - dependent upon if we use PRISM vs. Oracle
Note on H112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm approach for Sprint 4
Note on H149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to include the budget users (won't be in fed admin)
Note on M160: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential change for later based on oracle meeting @keehn, phyllis [Primary Key Solutions, LLC] @Smirniotopoulos, Jennifer @Hanayen, Rafaat [i360Technologies Inc]
Note on K161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential change for later based on oracle meeting @keehn, phyllis [Primary Key Solutions, LLC] @Smirniotopoulos, Jennifer @Hanayen, Rafaat [i360Technologies Inc]
Note on M161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential change for later based on oracle meeting @keehn, phyllis [Primary Key Solutions, LLC] @Smirniotopoulos, Jennifer @Hanayen, Rafaat [i360Technologies Inc]
Note on M162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potential change for later based on oracle meeting @keehn, phyllis [Primary Key Solutions, LLC] @Smirniotopoulos, Jennifer @Hanayen, Rafaat [i360Technologies Inc]

## BAS Program Sprint 3 Calendar
Business Applications Solution (BAS) Program
Common Solution Core Applications and Integration
Sprint 3 Calendar - April 2021 through June 2021
Session Attendee Information
Line # | Sprint | Workstream | Focus Area | Key Topics | Time | Date | Duration (Hours) | DOC BAS PMO | Decision Making Forum | Deep Dives | Configuration Validation
1 | 3 | Order to Cash (OTC) | Customer Refunds | Overview of Functionality Configuration Review Refunds process | 10 AM - 12 PM | 2021-04-01 | 2 | X | X | X
2 | 3 | PRISM | Post Award Management and Closeout Demo | • Processing funded and unfunded modifications • Sending and receiving files and messages through the FedConnect vendor portal • Viewing select financial data in PRISM • Loading and completing a closeout checklist • Closing awards in PRISM and Federal Procurement Data System (FPDS) | 10 AM - 12 PM | 2021-04-06 | 2 | X | X | X
3 | 3 | OTC | Intra-Government Payment and Collection (IPAC) Processing (Non-Inter-Agency Agreement (IAA) buy/sell) | Review Department of Commerce (DOC) IPAC transactions not related to buy/sell activity | 1 PM - 2 PM | 2021-04-07 | 1 | X | X |  | X
4 | 3 | OTC | Receipt Remittance | Overview of Functionality Configuration Review Receipt entry Remittance batch creation Reports | 10 AM - 12 PM | 2021-04-08 | 2 | X | X | X
5 | 3 | PRISM | Post Award Management and Closeout Workshop | • Determine the following information: - Closeout checklists - Additional post-award functionality | 10 AM - 12 PM | 2021-04-14 | 2 | X | X | X
6 | 3 | Procure to Pay (PTP) | Credit/Debit Memos/Refund Business Process | • Credit/Debit memo functionality in EBS • Bulk file of negative invoices (i.e. credit memos) • Refund business process | 1 PM - 3 PM | 2021-04-16 | 2 | X | X | X
7 | 3 | Projects | G-Invoicing (GINV) Interagency Agreements​: Servicing Agency | Review Policies related to IAA • Enter Agreement without Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | 1 PM - 3 PM | 2021-04-19 | 2 | X | X |  | X
8 | 3 | Integration | As-is Interface | As-Is Discovery NOAA 1 | 10 AM - 11 AM | 2021-04-20 | 1 | X
9 | 3 | Plan to Report (PTR) | Month End Close Process | • Month End Process • Standard PTR Reports | 1 PM - 3 PM | 2021-04-20 | 2 | X | X | X
10 | 3 | PTP | Receipts | • Review Receipt functionality in EBS | 10 AM - 12 PM | 2021-04-21 | 2 | X | X | X
11 | 3 | Integration | As-is Interface | As-Is Discovery NOAA 2 (As needed) | 10 AM - 11 AM | 2021-04-22 | 1 | X
12 | 3 | OTC | Deposits | Overview of Functionality Configuration Review Deposit Transactions Application of Receipts to Deposits Application of Deposit to Invoice Adjustment of Deposits Commitment Report | 10 AM - 12 PM | 2021-04-22 | 2 | X | X | X
13 | 3 | PRISM and Oracle E-Business Suite (EBS) | PRISM - EBS: Requisitions | • Review PRISM-EBS interface touchpoints for requisitions • Overview of the data flow from PRISM to EBS along PTP workstream • Impact of Data flow between interfaced platforms and BAS | 10 AM - 12 PM | 2021-04-27 | 2 | X | X | X
14 | 3 | PTR | Governmentwide Treasury Account Symbol (GTAS)/Digital Accountability and Transparency Act (DATA) Act Reporting | • GTAS Attributes • DATA Act Configurations • Reporting guidance across Department; bureau submission | 1 PM - 3 PM | 2021-04-28 | 2 | X | X | X
15 | 3 | OTC | Pay.gov (NOAA Only) | • Collections Information Repository (CIR) • Seafood Acceptable System/ Seafood Inspections Services Portal (SISP) | 1 PM - 3 PM | 2021-05-03 | 2 | X | X | X
16 | 3 | PRISM and EBS | PRISM - EBS: Awards | • Overview of the data flow from PRISM to EBS along PTP workstream • Impact of Data flow between interfaced platforms and BAS • Review PRISM-EBS interface touchpoints for awards | 1 PM - 4 PM | 2021-05-04 | 2 | X | X | X
17 | 3 | Projects | (GINV) Interagency Agreements​: Servicing Agency Pt. 2 | • Enter Agreement without Advance (Federal Customer)​; • Agreement fields (Mapping..) • Identification different Scenarios of IAA Non-Advance, • Revenue Budget • Selecting the Trading Partner and Validating Agency Location Code (ALC) and TAS​ • Capturing Performance Period and Budget Period for Incoming IAAs | 1 PM - 3 PM | 2021-05-05 | 2 | X | X |  | X
18 | 3 | Projects | (GINV) Create Funding | • Identify scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting | 1 PM - 3 PM | 2021-05-10 | 0.5 | X | X | X
19 | 3 | PTP | System for Award Management (SAM)/ Vendor Management | • Overview of Vendor Maintenance • SAM Interface Data Flow and Refresh • SAM/Non-SAM Vendors & Management/Maintenance • Financial Organization Master File (FOMF)/Oracle Payables Open Interface (APSI) | 10 - 12 PM | 2021-05-11 | 2 | X | X
20 | 3 | OTC | Pay.gov (NIST Only) | • Standard Reference Data (SRD) • Baldridge • Salesforce • Calibration Payment • Misc. Payment | 11 AM - 3 PM | 2021-05-12 | 3 | X | X | X
21 | 3 | PTR | Year End Close Process | • Year End Closing Definitions • Standard Year End Close Process | 1 PM - 3 PM | 2021-05-13 | 2 | X | X | X
22 | 3 | Projects | (GINV) Create Funding | • Identify scenarios of Funding Reimbursable IAA without Advance • Recognize Revenue and Billing: Billing method, Billing process • Billing and Revenue - Accounting | 1 PM - 3 PM | 2021-05-17 | 2 | X | X | X
23 | 3 | PTP | Travel (MLINQ/ Carlson Wagonlit Travel (CWT)/E2) | • CWT/E2/MLINQ <> EBS Interface Data Flow, Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the Travel process/etc. • Authorizations & Vouchers <> Obligations & Invoices • Discussion of unique travel transactions within the DOC | 1 PM - 3 PM | 2021-05-18 | 2 | X | X
24 | 3 | PRISM | Security Group Workshop | • Establish security groups and privileges | 1 PM - 5 PM | 2021-05-19 | 4 | X | X | X
25 | 3 | PTR | Budget Entry/Funds Status Report | • Budget Levels and Funds Control • Budget Execution transactions • Funds Check and Funds Status Report | 10 AM - 12 PM | 2021-05-20 | 2 | X | X |  | X
26 | 3 | PTR | Central Accounting Reporting System (CARS) and 224 Reconciliation Reports | • CARS Reporting • 224 Reconciliation Reports | 1 PM - 3 PM | 2021-05-24 | 2 | X | X |  | X
27 | 3 | PTP | Payment Automation Manager (PAM)/ Treasury Secure Payment System (SPS) | • PAM/SPS <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the PAM/SPS process/etc. • Overview of CTA (Classification Transactions + Accountability Process) and monthly accounting activity reports to Treasury | 1 PM - 3 PM | 2021-05-25 | 2 | X | X
28 | 3 | Integration | As-is Interface | As-Is Discovery NIST 1 | 10 AM - 11 AM | 2021-05-25 | 1 | X
29 | 3 | PRISM | Security Group Workshop | • Establish security groups and privileges | 1 PM - 5 PM | 2021-05-26 | 4 | X | X | X
30 | 3 | PTP | T-Card (SmartPay3) | • T-Card <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the T-Card process/etc. • Discuss unique scenarios for T-Card transactions and Reconciliation processes | 1 PM - 3 PM | 2021-05-27 | 2 | X | X | X
31 | 3 | Integration | As-is Interface | As-Is Discovery NIST 2 (As needed) | 10 AM - 11 AM | 2021-05-27 | 1 | X
32 | 3 | PTP | F-Card (SmartPay3) | • F-Card <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the F-Card process/etc. • Discuss unique scenarios for F-Card transactions and Reconciliation processes | 1 PM - 3 PM | 2021-06-01 | 2 | X | X
33 | 3 | PRISM | Reporting | • Review reporting requirements and PRISM capabilities | 1 PM - 3 PM | 2021-06-02 | 2 | X | X | X
34 | 3 | OTC | Customer Refunds | Overview of Functionality Configuration Review Refunds process | 1 PM - 3 PM | 2021-06-04 | 2 | X | X |  | X
35 | 3 | PTP | Receipts | • Review Receipt functionality in EBS | 10 AM - 12 PM | 2021-06-07 | 2 | X | X |  | X
36 | 3 | PTP | P-Card (SmartPay3) | • P-Card <> EBS Interface Data Flow; Design Expectations and User interaction • Conceptual discussion about where system checks will be/accounting details per the P-Card process/etc. • Discuss unique scenarios for P-Card transactions and Reconciliation processes | 1 PM - 3 PM | 2021-06-08 | 2 | X | X
37 | 3 | OTC | Receipt Remittance | Overview of Functionality Configuration Review Receipt entry Remittance batch creation Reports | 1PM-3PM | 2021-06-09 | 2 | X | X |  | X
38 | 3 | PTR | Month End Close Process | • Month End Process • Standard PTR Reports | 1 PM - 3 PM | 2021-06-10 | 2 | X | X |  | X
39 | 3 | PRISM or PTP | (GINV) G Invoicing Approach - Requesting Agency | Review PRISM Capabilities related to PRISM business process flows | 11 AM - 12 PM | 2021-06-14 | 2 | X | X | X
40 | 3 | PTP | Credit/Debit Memos/Refund Business Process | • Credit/Debit memo functionality in EBS • Bulk file of negative invoices (i.e. credit memos) • Refund business process | 1 PM - 3 PM | 2021-06-15 | 2 | X | X |  | X
41 | 3 | PRISM | Reporting | • Review reporting requirements and PRISM capabilities | 1 PM - 3 PM | 2021-06-16 | 2 | X | X |  | X
42 | 3 | PTP | Payroll | • Overview of integration to Payroll <> EBS, Data flow • Discuss current DOC requirements on Payroll practices | 1 PM - 3 PM | 2021-06-17 | 2 | X | X
43 | 3 | PTP | CTA | • Overview of CTA (Classification Transactions + Accountability Process) and monthly accounting activity reports to Treasury | 1 PM - 3 PM | 2021-06-18 | 2 | X | X | X
44 | 3 | Projects | (GINV) Interagency Agreements (Advance): Servicing Agency | • Enter Agreement with Advance (Federal Customer)​ • Agreement fields (Mapping..) • Identification current business cases for IAA With-Advance • Revenue Budget • Selecting the Trading Partner and Validating ALC and TAS​ • Accounting • Capturing Performance Period and Budget Period for Incoming IAAs | 1 PM - 3 PM | 2021-06-21 | 2 | X | X | X
45 | 3 | OTC | Deposits | Overview of Functionality Configuration Review Deposit Transactions Application of Receipts to Deposits Application of Deposit to Invoice Adjustment of Deposits Commitment Report | 1PM-3PM | 2021-06-22 | 2 | X | X |  | X
46 | 3 | Integration | As-is Interface | As-Is Discovery Census 1 | 10 AM - 11 AM | 2021-06-22 | 1 | X
47 | 3 | PRISM | Post Award Management and Closeout | • Processing funded and unfunded modifications • Sending and receiving files and messages through the FedConnect vendor portal • Viewing select financial data in PRISM • Loading and completing a closeout checklist • Closing awards in PRISM and FPDS | 10 AM - 12 PM | 2021-06-23 | 2 | X | X |  | X
48 | 3 | PTR | GTAS/DATA Act Reporting | • GTAS Attributes • DATA Act Configurations • Generating GTAS/DATA Act Reports | 10 AM - 12 PM 1 PM - 3 PM | 2021-06-24 | 4 | X | X |  | X
49 | 3 | Integration | As-is Interface | As-Is Discovery Census 2 (As needed) | 10 AM - 11 AM | 2021-06-24 | 1 | X
50 | 3 | PTP | Do-Not-Pay (DNP) Interface | • DNP Data flow to Treasury; EBS; PAM • Impact of Data flow between interfaced platforms and BAS | 10 AM - 12PM | 2021-06-25 | 2 | X | X
51 | 3 | PTR | Year End Close Process | • Year End Closing Definitions • Standard Year End Close Process | 1 PM - 3 PM | 2021-06-29 | 2 | X | X |  | X
52 | 3 | Projects | Reporting and Analysis (Cost and Expenditures) | Review Standard Oracle Reports related to cost and expenditures | 1 PM - 3 PM | 2021-06-30 | 2 | X | X | X
Note on H53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Patel, Darsh Did you mean for this to be 4 hours? Reply: Yes. Thank you.