## FY21 Q1 (hidden)
Department of Commerce FYs 2021/2022 Financial Statement Guidance
FY 2021 Q1 Due Date Calendar
GTAS reporting window: 1/7/2021 (8 AM ET) - 1/15/2021 (2 PM ET)
HFM reporting window: 1/4/2021 - 1/19/2021
Action | Attachment Reference | Responsible Party | Due Dates | Comments
All bureaus enter Improper Payments data into HFM. | K | All Bureaus | 1/4/21 to 1/11/21
All bureaus load into HFM and verify Preclose ETBs and Preclose supplemental data submissions. All bureaus enter into HFM DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 1/4/21 - 1/19/21
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events and GAAP Questionnaires. OFM will follow-up with bureaus, as needed. | A | All Bureaus | 2021-01-04
Stand-alone bureau (applicable to USPTO) submits to their Office of Civil Rights and respective human resources office inquiry letter on employee cases as of December 31. | F | USPTO | 2021-01-04
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | Servicing Bureaus | 2021-01-05
All bureaus submit to OFM unasserted claims through December 31 for the Department’s materiality threshold. | F | Servicing Bureaus | 2021-01-08
Applicable bureaus submit to NIST the shared TAS balances. | N/A | Servicing Bureaus | 2021-01-08 | Added.
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR & TSR. Please submit to USPTO by noon on January 8 . (If information is available sooner, please do not wait until the deadline to submit to partner bureaus.) | B | #REF! | 2021-01-08 | Updated to allow for 2-business days between preliminary and final.
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM copy of legal letter update through December 31. | F | OGC/OFM | 2021-01-11
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Agency Submission Form | C | All Bureaus | 2021-01-11
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2021-01-11
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, and actual FECA costs. (If data arrives before final financial statements preparation, OFM MAY adjust bureau data.) | N/A | OFM | 2021-01-11
All bureaus submit to OFM Preliminary Intragovernmental TDR for providing and receiving bureau transactions. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2021-01-11
OFM will generate and send out a draft GTAS vs HFM reconciliation to the bureaus. For Q1 Reporting purposes, explanations to the Draft Reconciliation will not be required but should be used as a tool to help resolve GTAS vs HFM differences prior to the closure of the two windows. | N/A | OFM | 2021-01-13
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. and submit to OFM Intra-Commerce Checklist Part I. | B | OFM | 2021-01-13
OFM submits to selected partner agencies Intragovernmental Providing and Receiving TDR and TSR. | C | OFM | 2021-01-14
Bureaus and OFM reconcile intragovernmental transactions with federal agencies. | C | Servicing Bureaus | 1/14/21 - 1/31/21
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). | N/A | Servicing Bureaus | 1/15/21 - 1/29/21
IGT Checklist Part I -- All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions, and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2021-01-21 | Changed due to Inauguration Day
OFM generates and sends out final GTAS vs HFM reconciliation to bureaus. | N/A | OFM | 2021-01-21 | Changed due to Inauguration Day
OFM reviews bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2021-01-21 | Changed due to Inauguration Day
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-level Summaries. OFM specifically identifies the category differences requiring corrections by bureaus. | B | OFM | 2021-01-21 | Changed due to Inauguration Day
All bureaus submit Review Checklist Part I to OFM. | A | All Bureaus | 2021-01-22 | Changed due to Inauguration Day
Bureaus respond to OFM review comments, and resolve any outstanding issues that may impact OFM’s LOCKDOWN of HFM ETB data, and the start of consolidated reporting. | N/A | All Bureaus | 2021-01-22 | Changed due to Inauguration Day
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2021-01-23 | Changed due to Inauguration Day
All bureaus submit to OFM the TROR (copy of actual submission), the TROR Certification, Verification, and Reconciliation, the TROR Transmittal Confirmation Report, and ALL variance explanations. | N/A | Servicing Bureaus | 2021-01-29
Checklist (Final) -- All bureaus submit to OFM the final, signed Review Checklists (complete), with bureau CFO Review Checklist signed by bureau CFO. *There are only two parts to the CFO Review Checklist in Q1. | A | All Bureaus | 2021-02-05 | *Subject to change based on CSC Data Act Dates
All bureaus submit to OFM F999 (Unidentified) explanations (AS REQUESTED BY OFM). OFM will follow up with bureaus on a case-by-case basis, if necessary | N/A | All Bureaus | TBD

## FY21 Q2 - DOC Schedule (hidden)
Department of Commerce FYs 2021/2022 Financial Statements Guidance
FY 2021 Q2 Due Date Calendar
GTAS reporting window: 4/6/2021 - 4/16/2021 at 2 PM EST
HFM reporting window: 4/1/2021 - 4/19/2021
Action | Attachment Reference | Responsible Party | Due Dates | Comments
OFM sends bureaus Quarterly Bureau Transactions/Events and GAAP Questionnaires. | N/A | OFM | 2021-03-05 | Completed
OFM e-mails bureaus a summary of significant new requirements/changes to the FS process. | N/A | OFM | 2021-03-05 | Completed
OFM e-mails bureaus the draft version of the Financial Statements Guidance for bureau comment. All bureaus provide any comments by March 12. | N/A | All Bureaus | 2021-03-08 | Completed
OFM e-mails bureaus the manual templates and the final version of the Financial Statements Guidance. | N/A | OFM | 2021-03-15 | Completed
All bureaus enter Improper Payments data into HFM. | K | Servicing Bureaus | 4/1/2021 - 4/12/2021
All bureaus load into HFM and verify Preclose ETBs and Preclose supplemental data submissions. All bureaus enter into HFM footnotes and DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 4/1/2021 - 4/19/2021
All bureaus canvass their program offices for all unasserted claims through Mar. 31. | F | All Bureaus | 2021-04-01
All bureaus submit OFM Quarterly Bureau GAAP Compliance Questionnaire. (OFM will follow-up with bureaus, as needed.) | A | All Bureaus | 2021-04-02
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events Questionnaire. (OFM will follow-up with bureaus, as needed.) | A | All Bureaus | 2021-04-02
Treasury GTAS IGT Reporting Window 2nd Quarter | N/A |  | April 6, 2021 8 a.m. – April 16, 2021 2 p.m.
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | Servicing Bureaus | 2021-04-07
Applicable bureaus submit to NIST the shared TAS balances. | N/A | Servicing Bureaus | 2021-04-07
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Agency Submission Form | C | All Bureaus | 2021-04-08
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR & TSR. Please submit to USPTO by noon on April 7 . (If information is available sooner, please do not wait until the deadline to submit to partner bureaus.) | B | Servicing Bureaus | 2021-04-08
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM copy of legal letter update through Mar 31. | F | OGC, OCR, USPTO | 2021-04-09
All bureaus submit to OFM Preliminary Intragovernmental TDR for providing and receiving bureau transactions. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2021-04-09
All bureaus submit to OFM unasserted claims through Mar 31 per the Department’s materiality threshold. | F | Servicing Bureaus | 2021-04-09
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2021-04-12
Applicable bureaus submit to OFM confirmation of Distributed Offsetting Receipts for April (cumulative fiscal year-to-date). | N/A | Servicing Bureaus | 2021-04-12
OFM submits to selected partner agencies Intragovernmental Providing and Receiving TDR and TSR. | C | OFM | 2021-04-12
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: Dates reflect Treasury’s open window period. The actual date for bureaus to finalize and certify the TROR and submit to OFM is April 30, 2021. | A | All Bureaus | 4/13/2021 - 4/30/2021
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. All bureaus submit Intra-Commerce Checklist Part I to OFM. | B | Servicing Bureaus | 2021-04-13
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, and actual FECA costs. (If data is not received in time, bureaus will estimate or default to prior SEP 30 data.) (If data arrives before final financial statements preparation, OFM MAY adjust bureau data.) | N/A | OFM | 2021-04-13
OFM will generate and send out a draft GTAS vs HFM reconciliation to the bureaus. The Draft Reconciliation should be used as a tool to help resolve GTAS vs HFM differences prior to the closure of the two windows. | N/A | Servicing Bureaus | 2021-04-15
OFM sends Distributed Offsetting Receipts for April (cumulative). | N/A | OFM | 2021-04-15
All bureaus submit Tie-points, SBR vs SF 132s comparison, Anomalies, F099 and F999 (Unidentified) difference explanations to OFM. | N/A | Servicing Bureaus | 2021-04-19
All bureaus submit International Agreements and Treaties Template to OFM. |  | All Bureaus | 2021-04-19 | Required per audit request
Stand-alone bureaus (applies to USPTO) submits stand-alone financial statements and footnotes. | A | USPTO | 2021-04-19
All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2021-04-20
OFM reviews bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2021-04-20
OFM prepares the Intra-Commerce Transaction Grids and High-level Summaries. OFM will identify any category differences and contact the impacted bureaus as necessary. | B | OFM | 2021-04-20
All bureaus submit Review Checklist Part I to OFM. | A | Servicing Bureaus | 2021-04-20
OFM will generate and send out the final GTAS vs HFM reconciliation to the bureaus. | N/A | Servicing Bureaus | 4/20/2021 (Noon)
Bureaus respond to OFM review comments and resolve any outstanding issues. | N/A | Servicing Bureaus | 2021-04-21
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2021-04-21
All bureaus submit to OFM explanations for significant financial statement fluctuations. Note: OFM may request additional explanations/information. | A | Servicing Bureaus | 2021-04-22
All bureaus submit Review Checklist Part II to OFM | A | Servicing Bureaus | 2021-04-23
OFM reviews bureaus’ fluctuation analysis and provides comments to bureaus. | N/A | OFM | 2021-04-23
Bureaus and OFM reconcile intragovernmental transactions with federal agencies. | C | OFM | 4/23/21 - 5/1/21
All bureaus submit to OFM the TROR (copy of actual submission), the TROR Certification, Verification, and Reconciliation, the TROR Transmittal Confirmation Report, and ALL variance explanations. | A | Servicing Bureaus | 2021-04-30
All bureaus submit to OFM final, signed Review Checklists (complete), with bureau CFO Review Checklist, Part III, signed by bureau CFO and financial manager. Date subject to change upon release of Q2 DATA Act schedule from the DOC DATA Act team. | A | All Bureaus | 2021-05-04

## FY21 Q3 (hidden)
Department of Commerce FYs 2021/2022 Financial Statements Guidance
FY 2021 Q3 Due Date Calendar
GTAS reporting window: 7/7/2021 (8 am) - 7/16/2021 (5 pm)
HFM reporting window: 7/1/2021 - 7/16/2021
Action | Attachment Reference | Responsible Party | Due Dates | Comments | 2021-07-01
OFM sends Quarterly Bureau Transactions/Significant Events and GAAP Questionnaires to bureaus. | A | OFM | 2021-06-01 | Completed | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
OFM e-mails bureaus a summary of significant new requirements/changes to the FS process. | A | OFM | 2021-06-15 | [5 empty] | 1 | 2 | 3
OFM e-mails bureaus the draft version of Financial Statements Guidance for bureau comment. | N/A | OFM | 2021-06-08 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10
OFM e-mails bureaus the manual templates and the final version of the Financial Statements Guidance. | N/A | OFM | 2021-06-15 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17
All bureaus canvass their program offices for all unasserted claims through June 30. | F | All Bureaus | 2021-07-01 |  | 18 | 19 | 20 | 21 | 22 | 23 | 24
All bureaus enter Improper Payments data into HFM. | K | Servicing Bureaus | 7/1/2021 - 7/12/2021 |  | 25 | 26 | 27 | 28 | 29 | 30 | 31
All bureaus load into HFM and verify Preclose ETBs and Preclose supplemental data submissions. All bureaus enter into HFM/DOL/OPM confirmation. All bureaus review/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 7/1/2021 – 7/16/2021
All bureaus enter required footnote data into HFM. All bureaus review/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. | K | Servicing Bureaus | 7/1/2021 – 7/16/2021
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events Questionnaire. OFM will follow-up with bureaus, as needed. | A | All Bureaus | 2021-07-02
All bureaus submit GAAP Compliance Questionnaire. OFM will follow-up with bureaus, as needed. | A | Servicing Bureaus | 2021-07-02
Treasury GTAS Budgetary & Proprietary Reporting Window | N/A | Servicing Bureaus | 7/7/2021 (8 am) – 7/16/2021 (5 pm)
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | NOAA, Census, USPTO, NTIS | 2021-07-08
Applicable bureaus submit to NIST the SHARED TAS GTAS templates. The Shared TAS data for DoC is reported in a consolidated file for GTAS. However, Shared TAS data for bureau balances must be submitted by bureau in Hyperion. Should be one day before the General Fund Entity Submission Form due date. | N/A | Servicing Bureaus | 2021-07-08
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR & TSR. Please submit to USPTO by noon on July 8 . (If information is available sooner, please do not wait until the deadline to submit to partner bureaus.) | B | NOAA, Census, NIST, NTIS | 2021-07-08
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Entity Submission Form. | C | All Bureaus | 2021-07-09
All bureaus submit to OFM unasserted claims through June 30 per the Department’s materiality threshold. | F | All Bureaus | 2021-07-09
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM copy of legal letter update through June 30. | F | USPTO/OFM | 2021-07-09
All bureaus submit to OFM Preliminary Intragovernmental TDR. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2021-07-09
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2021-07-12
OFM submits to selected partner agencies preliminary Intragovernmental Providing and Receiving TDR and TSR. | N/A | OFM | 2021-07-12
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, and actual FECA costs. (If data is not received in time, bureaus will estimate or default to prior September 30 data.) (If data arrives before final financial statements preparation, OFM MIGHT adjust bureau data.) | N/A | OFM | 2021-07-13
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. All bureaus submit Intra-Commerce Checklist Part I to OFM. | B | Servicing Bureaus | 2021-07-13 | *Submission date of 7/12/2021 to USPTO has been removed.
OFM will generate and send out a draft GTAS vs HFM reconciliation to the bureaus. The Draft Reconciliation should be used as a tool to help resolve GTAS vs HFM differences prior to the closure of the two windows. (3 days prior to HFM/GTAS closure.) | N/A | OFM | 2021-07-13
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: Dates reflect Treasury’s open window period. The actual date for bureaus to finalize and certify the TROR and submit to OFM is July 31, 2021. | A | Servicing Bureaus | 7/13/2021 – 7/30/2021
All bureaus: a) Enter SF 133s data into HFM St of BR vs. SF 133s Schedule b) Submit to OFM explanations for St of BR vs. SF 133s differences c) Email to OFM complete SF 133s d) Submit to OFM any journal entries resulting from SF-133 vs. ETB differences. | A | Servicing Bureaus | 7/15/2021 - 7/19/2021 | *Window closure date extended from 7/16/2021 to 7/19/2021
All bureaus submit to OFM explanations for tie-point differences (including BP tie-points). Bureaus are asked to use the BP Tie Point template for submitting explanations. | A | Servicing Bureaus | 2021-07-16
All bureaus submit to OFM explanations for SBR vs. SF132 comparison. Bureaus are asked to use the SBR vs SF 132 template for submitting explanations. | A | Servicing Bureaus | 2021-07-16
All bureaus submit to OFM all footnote data, to include: a) Manual footnotes data (Manual Template Data), if applicable b) Manual footnotes text matrix c) Manual RSI (excluding intragovernmental schedules), if applicable | A | Servicing Bureaus | 2021-07-16 | Note, Manual RSSI no longer required for Q3 Reporting. For Q4 reporting selected RSSI information will be included in MD&A.
All bureaus submit to OFM Review Checklists Part I signed by bureau Finance Manager (excluding Subsequent Review Checklist), with explanations for anomaly balances, net position analyses differences, and F999 (Unidentified) differences. Bureaus are asked to use the template for the Net Position Analyses explanations. | A | Servicing Bureaus | 2021-07-19 | *Date updated from 7/16/2021 to 7/19/2021
All bureaus submit International Agreements and Treaties Template to OFM. | N/A | All Bureaus | 2021-07-16
USPTO submits stand-alone financial statements and footnotes. | A | USPTO | 2021-07-19
All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2021-07-19
OFM reviews bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2021-07-19
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-Level Summaries for items requiring further analysis and/or corrective action. | B | OFM | 2021-07-19
OFM sends Distributed Offsetting Receipts for months of April - June for review. | N/A | OFM | 2021-07-19
Bureaus and OFM reconcile intragovernmental transactions with federal agencies | C | OFM/Applicable Servicing Bureaus | 7/19/2021 - 7/30/2021
OFM will generate and send out the final GTAS vs HFM reconciliation to the bureaus. | N/A | Servicing Bureaus | 2021-07-19
OFM reviews bureaus’ St of BR vs. SF 133s data/explanations and provides comments to bureaus. | N/A | Servicing Bureaus | 2021-07-19
Bureaus respond to OFM review comments and resolve any outstanding issues that may impact OFM’s LOCKDOWN of HFM ETB data, and the start of consolidated reporting. | N/A | All Bureaus as Needed | 2021-07-20 | If comments are provided sooner, please respond within 1 business day. This will allow consolidated reporting to begin sooner.
All bureaus submit to OFM explanations for all final differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2021-07-21
Treasury GTAS IGT Bulk Submission Deadline | N/A | Servicing Bureaus | 2021-07-21
All bureaus submit to OFM explanations for significant financial statement and footnote fluctuations. | A | Servicing Bureaus | 2021-07-21
Applicable bureaus submit to OFM confirmation regarding Distributed Offsetting Receipts for months of April – June (Q3). | N/A | Servicing Bureaus | 2021-07-22
All bureaus submit to OFM signed Review Checklists (including Subsequent Review Checklist), with CFO Review Checklist Part II signed by bureau Finance Manager. | A | All Bureaus | 2021-07-22
OFM reviews bureaus’ statement and footnote fluctuation analyses and provides comments to bureaus. | A | Servicing Bureaus | 2021-07-22
OFM submits unaudited financial statements to OMB 21 business days after Q3 close. | A | OFM | 2021-07-30
All bureaus submit to OFM the TROR (copy of actual submission), the TROR Certification, Verification, and Reconciliation, the TROR Transmittal Confirmation Report. *Due Date matches Treasury deadlines | A | Servicing Bureaus | 2021-07-30 | TROR window is 7/13/2021 - 7/31/2021. Due date adjusted to 7/30/2021 since 7/31/2021 is on a Saturday.
All bureaus submit to OFM final, signed Review Checklists (complete), with bureau CFO Review Checklist, Part III, signed by bureau CFO. | A | All Bureaus | 2021-08-06
OFM submits to Consolidated IPA Department’s financial statements, footnotes, RSI, RSSI, consolidating financial statement supporting schedules, trial balances, and intra-Commerce TSRs. | N/A | OFM | Various Dates (Late July/Early August)
OFM submits to OMB unaudited notes, RSI, RSSI, and OI and comparative significant variance analyses for the Balance Sheet, SNC, and SCNP no later than 45 business days after Q3 close. | A | OFM | 2021-08-09

## FY21 Q4
Department of Commerce FYs 2021/2022 Financial Statements Guidance
FY 2021 Q4 Due Date Calendar | [6 empty] | 2021-10-01
[7 empty] | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
GTAS reporting window: 10/6/2021 (8 AM) - 10/18/2021 (5 PM) | [11 empty] | 1 | 2
HFM reporting window: 10/1/2021 - 10/11/2021 | [6 empty] | 3 | 4 | 5 | 6 | 7 | 8 | 9
OFM will be providing bureau assistance and Hyperion Coverage October 9, 10, 11 and working fully October 16-17, 2021. Data call to come for bureau POC contacts on those dates. | [6 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16
Action | Attachment Reference | Responsible Party | Due Dates | Comments | General Guidelines |  | 17 | 18 | 19 | 20 | 21 | 22 | 23
OFM sends Quarterly Bureau Transactions/Events and GAAP Questionnaires to bureaus. | A | OFM | 2021-09-02 | Completed |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
OFM e-mails bureaus a summary of significant new requirements/changes to the Financial Statement Process. | A | OFM | 2021-09-09 |  | OFM e-mails bureaus summary of significant new requirements/changes by the 5th business day of the last month of each quarter: Dec (Q1), Mar (Q2), Jun (Q3), and Sep (year-end). |  | 3 10 17 24: 31
OFM e-mails bureaus the DRAFT version of the Financial Statements Guidance for bureau comment. | N/A | OFM | 2021-09-08 |  | OFM e-mails bureaus draft verion of Financial Statements Guidance by the 8th calendar day of the last month of each quarter, and allows time for bureaus to comment.
OFM e-mails bureaus the manual templates and the FINAL version of the Financial Statements Guidance. | N/A | OFM | 2021-09-15 |  | OFM e-mails bureaus manual templates and final version of Financial Statement Guidance by the 15th calendar day of the last month of each quarter.
All bureaus enter Improper Payments data into HFM. | K | All Bureaus | 10/1/2021 - 10/7/2021 |  | N/A
All bureaus load into HFM and verify Preclose ETBs and PreClose supplemental data submissions. All bureaus enter into HFM footnotes and DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 10/1/2021 - 10/10/2021 |  | Bureaus’ HFM window period –1st to 18th of reporting month for Q1 to Q2, 1st to 15th of reporting month for Q3, and 1st to approximately 10th day of reporting month for Q4. This is subject to change based on the GTAS reporting window as well as audit deadlines.
All bureaus canvass their program offices for all unasserted claims through September 30. | F | All Bureaus | 2021-10-01 |  | All bureaus canvass their program offices for all unasserted claims as of quarter or year-end; 1 business day after the end of the quarter.
Bureaus submit GAAP Compliance Questionnaires. OFM will follow-up with bureaus, as needed. | A | Servicing Bureaus | 2021-10-01 |  | Quarterly Bureau Questionnaire for Compliance with GAAP are due 1 or 2 business days after the end of the quarter.
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events templates. OFM will follow-up with bureaus, as needed. | A | All Bureaus | 2021-10-01 |  | Quarterly Bureau Events/Significant Transactions Questionnaires are due 1 or 2 business days after the end of the quarter.
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | NOAA, Census, USPTO, NTIS | 2021-10-05 |  | Bureaus’ DM/G&B trial balances to NIST – 5th business day of reporting month; earlier for Q4.
Applicable bureaus submit to NIST the SHARED TAS GTAS templates. * The Shared TAS data for DoC is reported in a consolidated file for GTAS. However, Shared TAS data for bureau balances must be submitted by bureau in Hyperion. | N/A | NOAA, Census, USPTO, NTIS | 2021-10-06 |  | N/A
All bureaus submit to OFM Preliminary Intra-governmental TDR for providing and receiving bureau transactions. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2021-10-06 |  | Bureaus’ Preliminary Intragovernmental TDR – by the 10th (calendar day) of the reporting month. For Q4, bureaus should provide the prelim TDR by the fourth business day, due to decreased reconciliation time with trading partners.
OFM sends preliminary GTAS v HFM reconciliation to bureaus (In Q4 the Final GTAS vs HFM reconciliation will be sent to bureaus following the close of the HFM Reporting window to ensure that there are no remaining differences between GTAS and HFM). | N/A | OFM | 2021-10-07 |  | N/A
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR and TSR. * Please submit to USPTO by noon on 10/6/2021. | B | Servicing Bureaus | 2021-10-06 |  | Bureaus’ Preliminary Intra-Commerce TDR/TSR – 6th business day of reporting month. Earlier in Q4. | *Requested 10/6/2021 by NOAA
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2021-10-07 |  | N/A
Applicable bureaus submit updates on recaptures of improper payments; OFM will have sent out a data call in September to the necessary parties. | K | Servicing Bureaus | 2021-10-07 |  | N/A
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Entity Submission Form. | C | All Bureaus | 2021-10-08 |  | N/A
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. All bureaus submit Intra-Commerce Checklist Part I to OFM. | B | Servicing Bureaus | 2021-10-08 |  | Bureaus’ Reconciled Intra-Commerce TDR/TSR – 3 days after due date for Preliminary Intra-Commerce TDR/TSR. Earlier for Q4.
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, actual FECA costs, and Actuarial FECA Liability breakdown by bureau. (If data is not received in time, bureaus will estimate. If data arrives before final financial statements preparation, OFM may adjust bureau data.) | N/A | OFM | 2021-10-08 |  | OFM provides bureaus with data for pensions, Treasury Judgment Fund payments, actual FECA costs, and, for year-end, Actuarial FECA Liability – 13th calendar day of the reporting month, or earlier if available (especially for Q4).
All bureaus submit to OFM unasserted claims through September 30 per the Department’s materiality threshold. | F | Servicing Bureaus | 2021-10-08 |  | All bureaus submit to OFM unasserted claims per the Department’s materiality threshold as of quarter or year-end – 8th business day of the reporting month. Earlier for Q4.
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM a copy of initial legal letter response as of September 30. | F | OGC/OCR/USPTO | 2021-10-08 |  | N/A
OFM sends Distributed Offsetting Receipts for months of July - September for review. | N/A | OFM | 2021-10-08 |  | N/A
Bureaus submit Treaties and International Agreements Templates. OFM will follow-up with bureaus, as needed. All bureaus must complete and submit a template - see instructions in template for negative confirmations. | N/A | All Bureaus | 2021-10-10 |  | N/A
Digital Asset Template is due to OFM. | N/A | Servicing Bureaus | 2021-10-10 |  | New line. Was a data call last year.
All bureaus submit to OFM: a) Manual footnotes text matrix b) Explanations for tie-point differences, including BP tie-points, and SBR vs SF 132s comparison, if applicable. Bureaus are asked to use the new BP Tie point and SBR vs SF 132 for submitting explanations. c) Manual footnotes data (Loans Receivable Prior Period Adjustments, Note 20, Note 21 NEW and Note 23, Prior Period Adjustment), if applicable d) Manual RSI (excluding intragovernmental schedules), if applicable e) Manual RSSI, if applicable. | A | Servicing Bureaus | 2021-10-11 |  | Bureaus’ manual submissions – same due date as end of HFM window period.
All bureaus submit explanations for anomaly balances, net position analyses differences, and F999 (Unidentified). | A | Servicing Bureaus | 2021-10-11 |  | Bureaus’ manual submissions – same due date as end of HFM window period.
USPTO submits stand-alone financial statements and footnotes. | A | USPTO | 2021-10-12 |  | N/A
All bureaus submit Review Checklist Part I to OFM signed by bureau Finance Manager (excluding Subsequent Review Checklist). | A | All Bureaus | 2021-10-12 |  | Bureaus’ Review Checklists Part I signed by Finance Managers, with explanations for Net Position Analyses and Anomaly balances – 1 business day after HFM window period.
All bureaus submit to OFM their audit adjusted Intra-governmental TDR (final) for providing and receiving bureau transactions and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2021-10-11 |  | For FY 21, Q4 reporting - due same day as HFM window closes in order to provide final data to trading partners for Year-End Close Out.
OFM reviews Bureaus’ data, reports, and manual submissions; provides comments to bureaus. | N/A | OFM | 2021-10-12 |  | OFM reviews bureaus’ data/reports – 1 business day after end of HFM window period.
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-level Summaries. OFM specifically identifies the category differences requiring corrections by bureaus. | B | OFM | 2021-10-12 |  | OFM issues Intra-Commerce grids/differences requiring follow-up to bureaus– 1 business day after end of HFM window period.
OFM sends Final GTAS v HFM reconciliation to bureaus. Any additional GTAS differences made by bureaus following the close of the ETB Reporting window must be communicated and approved by OFM as all differences will be shown in Footnote 28, Reclassified Statements. | N/A | OFM | 2021-10-12 |  | OFM sends final GTAS v HFM recon the day after HFM closes.
Bureaus respond to OFM review comments, and resolve any outstanding issues that may impact OFM’s LOCKDOWN of HFM ETB data, and the start of consolidated reporting. | N/A | All Bureaus (as needed) | 2021-10-13 |  | Bureaus respond to OFM review comments no more than one day after OFM provides them.
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2021-10-13 |  | Bureaus provide explanations for final GTAS v HFM recon differences no later than one day after OFM provides the reconciliations.
All bureaus submit explanations for significant financial statement and footnote fluctuations to OFM. | A | Servicing Bureaus | 10/14/2021 (NOON) |  | Bureaus’ fluctuation explanations are due 3 business days after end of HFM window period. Earlier for Q4 due to audit deadlines, and financial statement preparation.
OFM reviews bureaus’ fluctuation analyses and provides comments to bureaus. | N/A | OFM | 10/14/2021 (End of Day) |  | OFM reviews bureaus’ fluctuation explanations and provides comments – 1 day (possibly calendar for Q3 & Q4) after bureaus’ fluctuation explanations due date.
All bureaus: a) Enter SF 133s data into HFM St of BR vs. SF 133s Schedule b) Submit to OFM explanations/comments for SF 133s vs. St of BR analysis c) Email to OFM complete SF 133s (Also, include the overall summary at the bureau level). | A | Servicing Bureaus | 2021-10-13 |  | Bureaus’ window period for entering SF 133s into HFM – the beginning date is the calendar day after end of GTAS window period and lasts for two business days. Much earlier for Q4 due to audit deadlines.
Applicable bureaus submit to OFM confirmation regarding Distributed Offsetting Receipts for month of July - September | N/A | Servicing Bureaus | 2021-10-13 |  | N/A
OFM reviews bureaus’ St of BR vs. SF 133s data/explanations and provides comments to bureaus. | N/A | OFM | 2021-10-14 |  | OFM reviews SF-133 data no later than one day after bureaus submit.
All bureaus submit CFO Review Checklist Part II to OFM, signed by bureau Finance Manager. | A | All Bureaus | 2021-10-15 |  | Bureaus’ Review Checklists Part II signed by bureau Finance Managers – 4 business days after end of HFM window period. 4 calendar days for Q4.
All bureaus submit to partner bureaus Audit Adjusted Intra-Commerce TDR and TSR, and submit to OFM Intra-Commerce Checklist Part II. | B | All Bureaus | 2021-10-18 |  | N/A
DOC Draft Agency Financial Report including financial statements and footnotes due to auditors | A | OFM | 2021-10-19
Additional GTAS vs. HFM Reconciliation will be run following the close of the GTAS reporting window. Any additional differences between HFM and GTAS not previously identified and explained must be explained. | N. | Servicing Bureaus | 2021-10-19 |  | HFM vs. GTAS reconciliation will be sent by noon with explanations required for any new differences by COB.
All bureaus submit to OFM Intra-governmental Checklist Part II. | C | Servicing Bureaus | 2021-10-28
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: The Treasury window period ends Nov 12, 2021; however, bureaus’ window period needs to be accelerated to allow for OFM review of bureaus’ TROR data and to allow year-end reporting requirements. Due to year-end reporting requirements, the actual date for bureaus to finalize and certify the TROR and submit to OFM has been accelerated to 10/29/2021. | A | Servicing Bureaus | 2021-10-29 |  | N/A
All bureaus submit to OFM the final, signed Review Checklists (complete), with bureau CFO Review Checklist, Part III, signed by bureau CFO. | A | All Bureaus | 2021-11-05 |  | N/A
USPTO submits to OFM unasserted claims through November for the Department’s materiality threshold, as well as an email updated response to Heather Flanagan and Erik Causey for legal matters existing / effective no earlier than November 4, 2021. | F | USPTO | 11/5/2021 (noon) |  | Dates per legal letter request.
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit a copy of the updated/final legal letter response, as of November 9 to OFM and Heather Koppe Flanagan (hflanagan@kpmg.com). | F | OGC/OCR/USPTO | 11/10/2021 (noon) |  | Dates per legal letter request.
All bureaus submit to OFM unasserted claims through November 9 per the Department’s materiality threshold. | F | All Bureaus | 11/10/2020 (noon) |  | Dates per legal letter request.
Final AFR Published and submitted to OMB | A | OFM | 2021-11-15 |  | Dates per OMB-A-136.

## Notes & Guidelines
Department of Commerce FYs 2021/2022 Financial Statements Guidance
FY 2021 Due Date Calendar - Notes & Guidelines
Notes
1 | The due date calendar is arranged in chronological order.
2 | OFM will monitor bureaus' submissions against the due dates. A deadline may be considered not met if the data is incomplete, inaccurate, or not reconciled to other applicable data.
3 | Dates are subject to change if the requirement affects the timely completion of the audit or timely preparation of financial reporting/analyses requirements.
4 | The listing of General Guidelines Used to Prepare Due Dates is included below.
5 | Due dates includes estimates when actual dates are not yet known (estimated dates are in blue font). For example, Treasury may not have yet published all of its due date requirements (i.e. GTAS, TROR, and IFCS window periods).
6 | The Responsible Party column indicates who is responsible for completing a deliverable. Tasks completed by Census, USPTO, NTIS, NIST, and NOAA (as service providers) are identified as Servicing Bureaus. Tasks completed by ALL bureaus are identified as All Bureaus.
General Guidelines Used to Prepare Due Dates (arranged in due date chronological order):
1 | OFM e-mails bureaus summary of significant new requirements/changes by the 5th business day of the last month of each quarter: Dec (Q1), Mar (Q2), Jun (Q3), and Sep (year-end).
2 | OFM e-mails bureaus draft verion of Financial Statements Guidance by the 8th calendar day of the last month of each quarter, and allows time for bureaus to comment.
3 | OFM e-mails bureaus manual templates and final version of Financial Statement Guidance by the 15th calendar day of the last month of each quarter.
4 | Quarterly Bureau Events/Significant Transactions Questionnaires are due 1 or 2 business days after the end of the quarter.
5 | Quarterly Bureau Questionnaire for Compliance with GAAP are due 1 or 2 business days after the end of the quarter.
6 | All bureaus canvass their program offices for all unasserted claims as of quarter or year-end; 1 business day after the end of the quarter.
7 | All bureaus submit to OFM their General Fund Agency Submission Form with balances for their main accounts in reciprocal categories included on the form - 6th business day after the end of the quarter.
8 | Bureaus’ HFM window period –1st to 18th of reporting month for Q1 to Q2, 1st to 15th of reporting month for Q3, and 1st to approximately 10th day of reporting month for Q4. This is subject to change based on the GTAS reporting window as well as audit deadlines.
9 | Bureaus’ DM/G&B trial balances to NIST – 5th business day of reporting month.
10 | Bureaus’ Preliminary Intra-Commerce TDR/TSR – 6th business day of reporting month.
11 | Bureaus’ SF-133s for GSA Federal Buildings Fund to NIST and OFM – 7th business day of reporting month. (If required.)
12 | All bureaus submit to OFM unasserted claims per the Department’s materiality threshold as of quarter or year-end – 8th business day of the reporting month.
13 | Bureaus’ Reconciled Intra-Commerce TDR/TSR – 3 days after due date for Preliminary Intra-Commerce TDR/TSR.
14 | Bureaus’ Preliminary Intragovernmental TDR – by the 10th (calendar day) of the reporting month. For Q4, bureaus should provide the prelim TDR by the fourth business day.
15 | OFM provides bureaus with Distributed Offsetting Receipts (DOR) data on a quarterly basis for cumulative fiscal year-to-date activity up to the end of the last month of the quarter. Bureaus submit their DOR confirmation to OFM by 12th calendar day of the month.
16 | OFM provides bureaus with data for pensions, Treasury Judgment Fund payments, actual FECA costs, and, for year-end, Actuarial FECA Liability – 13th calendar day of the reporting month, or earlier if available.
17 | OFM is no longer required to reconcile differences with DOL using IFCS. Nevertheless, all differences will be reviewed during the scorecard meeting with Treasury. OFM will follow-up with bureaus as needed. Authoritative source balances for DOL/OPM will be posted to the Fiscal Service website: http://www.fms.treas.gov/closingpackage/reports.html each quarter on or around the fifth workday.
18 | Stand-alone bureau submits to their Office of Civil Rights and respective human resources office inquiry letter on employee cases as of quarter or year-end – 13th calendar day of reporting month.
19 | Stand-alone bureau submits to their Office of General Counsel legal inquiry letter as of quarter or year-end –13th calendar day of reporting month.
20 | Bureaus’ manual submissions – same due date as end of HFM window period.
21 | Bureaus’ Intragovernmental TDR – 1 business day after end of HFM window period.
22 | Bureaus’ Review Checklists Part I signed by Finance Managers, with explanations for Net Position Analyses and Anomaly balances – 1 business day after HFM window period.
23 | OFM reviews bureaus’ data/reports – 1 business day after end of HFM window period.
24 | OFM issues Intra-Commerce grids/differences requiring follow-up to bureaus– 1 business day after end of HFM window period.
25 | Bureaus’ fluctuation explanations – 3 business days after end of HFM window period.
26 | OFM reviews bureaus’ fluctuation explanations and provides comments – 1 day (possibly calendar for Q3 & Q4) after bureaus’ fluctuation explanations due date.
27 | Bureaus’ TROR window period – if/when Treasury has not yet published actual dates, estimates are 15th to 30th for Q1 to Q3; 15th – 20th for year-end. NOTE: For year-end, bureaus’ window period is shorter than Treasury’s window period because of year-end audit timeline.
28 | Bureaus’ Review Checklists Part II signed by bureau Finance Managers – 4 business days after end of HFM window period.
29 | Bureaus submit TROR copy, certification, verification, & reconciliation, and transmittal confirmation report to OFM –no later than the end of bureaus’ TROR window period for Q1-Q3. For year-end, due dates MAY be accelerated more due to the audit timeframe.
30 | OFM submits to Consolidated IPA Department’s fluctuation analyses, net position analyses, and tie-point reports – 8 business days after OFM submits full financial statements to Consolidated IPA.
31 | Bureaus’ window period for entering SF 133s into HFM – the beginning date is the calendar day after end of GTAS window period and lasts for two business days.
32 | OFM reviews bureaus’ St of BR vs. SF 133s data/explanations and provides comments to bureaus – 1 business day after closure of bureaus HFM window for SF133 entry.
33 | Bureaus’ Review Checklists Part III signed by bureau CFO –Due date dependent upon DATA Act Certification due dates.
34 | OFM submits to Consolidated IPA Department’s TROR and Reconciliation – 11 business days after bureaus submit TROR information to OFM for Q1 to Q3

## FY21 GTAS Schedule
FY 2021 GTAS Reporting Window Schedule
Budgetary and Proprietary Reporting |  |  | Intragovernmental Reporting
Period End | Period | Reporting Window | Extension Request Deadline | Bulk File Submission Due Dates | Material Difference Reporting Window
2020-11-30 | November | Friday, December 4, 2020, 8 a.m. ET Thursday, December 17, 2020, 2 p.m. ET
2020-12-31 | December | Thursday, January 7, 2021, 8 a.m. ET Saturday, January 16, 2021, 2 p.m. ET | Tuesday, January 19, 2021, 5 p.m. ET | Thursday, January 21, 2021, 5 p.m. ET | Monday, January 25, 2021, 8 a.m. ET Friday, January 29, 2021, 5 p.m. ET
2021-01-31 | January | Thursday, February 4, 2021, 8 a.m. ET Thursday, February 18, 2021, 2 p.m. ET
2021-02-28 | February | Thursday, March 4, 2021, 8 a.m. ET Thursday, March 18, 2021, 2 p.m. ET
2021-03-31 | March | Tuesday, April 6, 2021, 8 a.m. ET Friday, April 16, 2021, 2 p.m. ET | Monday, April 19, 2021, 5 p.m. ET | Wednesday, April 21, 2021, 5 p.m. ET | Friday, April 23, 2021, 8 a.m. ET Thursday, April 29, 2021, 5 p.m. ET
2021-04-30 | April | Thursday, May 6, 2021, 8 a.m. ET Tuesday, May 18, 2021, 2 p.m. ET
2021-05-31 | May | Friday, June 4, 2021, 8 a.m. ET Thursday, June 17, 2021, 2 p.m. ET
2021-06-30 | June | Wednesday, July 7, 2021, 8 a.m. ET Friday, July 16, 2021, 5 p.m. ET | Monday, July 19, 2021, 5 p.m. ET | Wednesday, July 21, 2021, 5 p.m. ET | Friday, July 23, 2021, 8 a.m. ET Thursday, July 29, 2021, 5 p.m. ET
2021-07-31 | July | Thursday, August 5, 2021, 8 a.m. ET Wednesday, August 18, 2021, 5 p.m. ET
2020-08-31 | August | Tuesday, September 7, 2021, 8 a.m. ET Thursday, September 16, 2021, 5 p.m. ET
2021-09-30 | September | Wednesday, October 6, 2021, 8 a.m. ET *Monday, October 18, 2021, 5 p.m. ET* | N/A | Monday, October 18, 2021, 5 p.m. ET | N/A
Period 12 Revision Window |  | Monday, October 18, 2021, 8 p.m. ET Thursday, November 4, 2021, 5 p.m. ET | Monday, November 8, 2021, 5 p.m. ET | Friday, November 12, 2021, 2 p.m. ET | TBD
Notes:
1) The FY 2020 reporting window schedule is based on OMB Circular No. A-11, Section 130.2(e).
2) The Bureau of the Fiscal Service will require all TAS to be reported in each reporting window, including double zero's.
3) Certified agency bulk files submitted during the reporting window will be used to derive the quarterly intragovernmental reporting data. NOTE: Only certified data is used for Intragovernmental Reporting.
4) * Agencies must certify Expenditure TAS NLT October 18, 2021, 5 p.m. ET. OMB will import submissions as of this date into the PY column of the Budget Schedule P. Agencies may revise this data later in the window but must coordinate changes with their budget offices to ensure agreement between GTAS submissions and the Budget.
5) The times included on the reporting window schedule represent when the bulk file flag will be turned on/off. The system will always be available for reports and analytics.
6) Fiscal Service will extract certified TAS balances October 18, 2021 after 5 p.m. ET for use in the Pre-Year-End Summary Report.
7) Fiscal Service will require Material Difference Explanations via GTAS for the final GTAS Submission; therefore, the differences that are required to be explained per I TFM 2-4700, Sections 4706.10 through 4706.45 will be done via GTAS during the Material Difference Reporting Window. The differences and required explanations will be based upon the final certified data present in the system on November 12, 2021.

## YE 2021 - Post Close (hidden)
Department of Commerce FYs 2020/2021 Financial Statements Guidance
FY 2020 - Post Close Due Date Calendar
Action | Attachment Reference | Responsible Party | Due Dates
All bureaus notify OIG, IPAs, and OFM of scheduled PP&E and inventory counts. | A | Servicing Bureaus | When Known
All bureaus load into HFM final Postclose ETBs and Postclose Balance Sheet Split SGL Accounts supplemental data submissions. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 11/24/2020 to 12/4/2020
OFM e-mails bureaus the draft version of the Financial Statements Guidance for bureau comment. | N/A | OFM | 2020-12-07
OFM e-mails bureaus the manual templates and the final version of the Financial Statements Guidance. | N/A | OFM | 2020-12-14
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit an updated email legal letter response (Government-wide update) as of Jan 22 to Patricia McBarnette, DOC OIG, with a cc to OFM. | G, K | OGC, OCR, USPTO | 2021-01-25