## Notes & Guidelines
Department of Commerce FYs 2020/2021 Financial Statements Guidance
FY 2020 Due Date Calendar - Notes & Guidelines
Notes
1 | The due date calendar is arranged in chronological order.
2 | OFM will monitor bureaus' submissions against the due dates. A deadline may be considered not met if the data is incomplete, inaccurate, or not reconciled to other applicable data.
3 | Dates are subject to change if the requirement affects the timely completion of the audit or timely preparation of financial reporting/analyses requirements.
4 | The listing of General Guidelines Used to Prepare Due Dates is included below.
5 | Due dates includes estimates when actual dates are not yet known (estimated dates are in blue font). For example, Treasury may not have yet published all of its due date requirements (i.e. GTAS, TROR, and IFCS window periods).
6 | The Responsible Party column indicates who is responsible for completing a deliverable. Tasks completed by Census, USPTO, NTIS, NIST, and NOAA (as service providers) are identified as Servicing Bureaus. Tasks completed by ALL bureaus are identified as All Bureaus.
General Guidelines Used to Prepare Due Dates (arranged in due date chronological order):
1 | OFM e-mails bureaus summary of significant new requirements/changes by the 5th business day of the last month of each quarter: Dec (Q1), Mar (Q2), Jun (Q3), and Sep (year-end).
2 | OFM e-mails bureaus draft verion of Financial Statements Guidance by the 8th day of the last month of each quarter, and allows time for bureaus to comment.
3 | OFM e-mails bureaus manual templates and final version of Financial Statement Guidance by the 15th day of the last month of each quarter.
4 | Quarterly Bureau Events/Significant Transactions Questionnaires are due 1 or 2 business days after the end of the quarter.
5 | Quarterly Bureau Questionnaire for Compliance with GAAP are due 1 or 2 business days after the end of the quarter.
6 | All bureaus canvass their program offices for all unasserted claims as of quarter or year-end; 1 business day after the end of the quarter.
7 | All bureaus submit to OFM their General Fund Agency Submission Form with balances for their main accounts in reciprocal categories included on the form - 6th business day after the end of the quarter.
8 | Bureaus’ HFM window period –1st to 18th of reporting month for Q1 to Q2, 1st to 15th of reporting month for Q3, and 1st to 11th of reporting month for Q4. HFM window closing on the 17th for FY 19, Q1 to align with the closing of the Treasury GTAS reporting window.
9 | Bureaus’ DM/G&B trial balances to NIST – 5th of the reporting month
10 | Bureaus’ Preliminary Intra-Commerce TDR/TSR – 6th of the reporting month
11 | Bureaus’ SF-133s for GSA Federal Buildings Fund to NIST and OFM – 7th of the reporting month. If required.
12 | All bureaus submit to OFM unasserted claims per the Department’s materiality threshold as of quarter or year-end – 8th of the reporting month
13 | Bureaus’ Reconciled Intra-Commerce TDR/TSR – 3 days after due date for Preliminary Intra-Commerce TDR/TSR
14 | Bureaus’ Preliminary Intragovernmental TDR – by the 10th of the reporting month, each Quarter
15 | OFM provides bureaus with Distributed Offsetting Receipts (DOR) data on a quarterly basis for cumulative fiscal year-to-date activity up to the end of the last month of the quarter. Bureaus submit their DOR confirmation to OFM by 12th of the month.
16 | OFM provides bureaus with data for pensions, Treasury Judgment Fund payments, actual FECA costs, and, for year-end, Actuarial FECA Liability – 13th of the reporting month, or earlier if available.
17 | OFM is no longer required to reconcile differences with DOL using IFCS. Nevertheless, all differences will be reviewed during the scorecard meeting with Treasury. OFM will follow-up with bureaus as needed. Authoritative source balances for DOL/OPM will be posted to the Fiscal Service website: http://www.fms.treas.gov/closingpackage/reports.html each quarter on or around the fifth workday.
18 | Stand-alone bureau submits to their Office of Civil Rights and respective human resources office inquiry letter on employee cases as of quarter or year-end – 13th of the reporting month.
19 | Stand-alone bureau submits to their Office of General Counsel legal inquiry letter as of quarter or year-end –13th of reporting month.
20 | Bureaus’ manual submissions – same due date as end of HFM window period.
21 | Bureaus’ Intragovernmental TDR – 1 business day after end of HFM window period.
22 | Bureaus’ Review Checklists Part I signed by Finance Managers, with explanations for Net Position Analyses and Anomaly balances – 1 business day after HFM window period.
23 | OFM reviews bureaus’ data/reports – 1 business day after end of HFM window period.
24 | OFM issues Intra-Commerce grids/differences requiring follow-up to bureaus– 1 business day after end of HFM window period.
25 | Bureaus’ fluctuation explanations – 3 business days after end of HFM window period.
26 | OFM reviews bureaus’ fluctuation explanations and provides comments – 1 calendar day after bureaus’ fluctuation explanations due date.
27 | Bureaus’ TROR window period – if/when Treasury has not yet published actual dates, estimates are 15th to 30th for Q1 to Q3; 15th – 20th for year-end. NOTE: For year-end, bureaus’ window period is shorter than Treasury’s window period because of year-end audit timeline.
28 | Bureaus’ Review Checklists Part II signed by bureau Finance Managers – 4 business days after end of HFM window period.
29 | Bureaus submit TROR copy, certification, verification, & reconciliation, and transmittal confirmation report to OFM –no later than the end of bureaus’ TROR window period for Q1-Q3. For year-end, due dates MAY be accelerated more due to the audit timeframe.
30 | OFM submits to Consolidated IPA Department’s fluctuation analyses, net position analyses, and tie-point reports – 8 business days after OFM submits full financial statements to Consolidated IPA.
31 | Bureaus’ window period for entering SF 133s into HFM – the beginning date is the calendar day after end of GTAS window period and lasts for two business days.
32 | OFM reviews bureaus’ St of BR vs. SF 133s data/explanations and provides comments to bureaus – 1 business day after closure of bureaus HFM window for SF133 entry.
33 | Bureaus’ Review Checklists Part III signed by bureau CFO –Due date dependent upon DATA Act Certification due dates.
34 | OFM submits to Consolidated IPA Department’s TROR and Reconciliation – 11 business days after bureaus submit TROR information to OFM for Q1 to Q3

## YE 2019 - Post Close
Department of Commerce FYs 2020/2021 Financial Statements Guidance
FY 2019 - Post Close Due Date Calendar
Action | Attachment Reference | Responsible Party | Due Dates
All bureaus notify OIG, IPAs, and OFM of scheduled PP&E and inventory counts. | A | Servicing Bureaus | When Known
All bureaus load into HFM final Postclose ETBs and Postclose Balance Sheet Split SGL Accounts supplemental data submissions. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 11/26/2019 to 12/6/2019
OFM e-mails bureaus the draft version of the Financial Statements Guidance for bureau comment. | N/A | OFM | 2019-12-06
OFM e-mails bureaus the manual templates and the final version of the Financial Statements Guidance. | N/A | OFM | 2019-12-13
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit an updated email legal letter response (Government-wide update) as of Jan 22 to Patricia McBarnette, DOC OIG, with a cc to OFM. | G, K | OGC, OCR, USPTO | 2020-01-24

## FY20 Q1
Department of Commerce FYs 2020/2021 Financial Statements Guidance
FY 2020 Q1 Due Date Calendar
GTAS reporting window: 1/7/2020 8 AM EST - 1/16/2020 2 PM EST
HFM reporting window: 1/2/2020 - 1/17/2020
Action | Attachment Reference | Responsible Party | Due Dates | Comments
All bureaus enter Improper Payments data into HFM. | K | All Bureaus | 1/2/2020 to 1/10/2020
All bureaus load into HFM and verify Preclose ETBs and Preclose supplemental data submissions. All bureaus enter into HFM DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 1/2/2020 - 1/17/2020
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events and GAAP Questionnaires. OFM will follow-up with bureaus, as needed. | A | All Bureaus | 2020-01-03
Stand-alone bureau (applicable to USPTO) submits to their Office of Civil Rights and respective human resources office inquiry letter on employee cases as of December 31. | F | USPTO | 2020-01-03
All bureaus submit to OFM unasserted claims through December 31 for the Department’s materiality threshold. | F | Servicing Bureaus | 2020-01-08
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | NOAA, Census, USPTO, NTIS | 2020-01-08
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM copy of legal letter update through December 31. | F | OGC/OFM | 2020-01-09
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Agency Submission Form | C | All Bureaus | 2020-01-09
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR & TSR. Please submit to USPTO by noon on January 8 . (If information is available sooner, please do not wait until the deadline to submit to partner bureaus.) | B | Servicing Bureaus | 2020-01-09
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2020-01-10
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. and submit to OFM Intra-Commerce Checklist Part I. | B | Servicing Bureaus | 2020-01-14
OFM will generate and send out a draft GTAS vs HFM reconciliation to the bureaus. For Q1 Reporting purposes, explanations to the Draft Reconciliation will not be required but this should be used as a tool to help resolve GTAS vs HFM differences prior to the closure of the two windows. | N/A | Servicing Bureaus | 2019-01-15
All bureaus submit to OFM Preliminary Intragovernmental TDR for providing and receiving bureau transactions. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2020-01-15
All bureaus submit to OFM the TROR (copy of actual submission), the TROR Certification, Verification, and Reconciliation, the TROR Transmittal Confirmation Report, and ALL variance explanations. | N/A | Servicing Bureaus | 2020-01-31
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). | N/A | Servicing Bureaus | 1/15/2020 - 1/31/2020
All bureaus submit Review Checklist Part I to OFM. | A | All Bureaus | 2019-01-21
IGT Checklist Part I -- All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions, and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2019-01-21
OFM reviews bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2020-01-21
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-level Summaries. OFM specifically identifies the category differences requiring corrections by bureaus. | B | OFM | 2020-01-21
Bureaus respond to OFM review comments, and resolve any outstanding issues that may impact OFM’s LOCKDOWN of HFM ETB data, and the start of consolidated reporting. | N/A | All Bureaus | 2020-01-23
Bureaus and OFM reconcile intragovernmental transactions with federal agencies. | C | Servicing Bureaus | 1/23/2020 - 1/30/2020
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2020-01-24
OFM submits to selected partner agencies Intragovernmental Providing and Receiving TDR and TSR. | C | OFM | 2/6/2020 or earlier
Checklist (Final) -- All bureaus submit to OFM the final, signed Review Checklists (complete), with bureau CFO Review Checklist signed by bureau CFO. *There are only two parts to the CFO Review Checklist in Q1. | A | All Bureaus | 2020-02-07 | *Subject to change based on CSC Data Act Dates
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, and actual FECA costs. (If data is not received in time, bureaus will estimate or default to prior SEP 30 data.) (If data arrives before final financial statements preparation, OFM MAY adjust bureau data.) | N/A | OFM | TBD
All bureaus submit to OFM F999 (Unidentified) explanations (AS REQUESTED BY OFM). OFM will follow up with bureaus on a case-by-case basis, if necessary | N/A | All Bureaus | TBD

## FY20 Q2
Department of Commerce FYs 2020/2021 Financial Statements Guidance
FY 2020 Q2 Due Date Calendar
GTAS reporting window: 4/6/2020 - 4/16/2020 at 2 PM EST
HFM reporting window: 4/1/2020 - 4/17/2020
Action | Attachment Reference | Responsible Party | Due Dates | Comments
OFM sends bureaus Quarterly Bureau Transactions/Events and GAAP Questionnaires. | N/A | OFM | 2020-03-06 | Complete
OFM e-mails bureaus a summary of significant new requirements/changes to the FS process. | N/A | OFM | 2020-03-06 | Completed
OFM e-mails bureaus the draft version of the Financial Statements Guidance for bureau comment. All bureaus provide any comments by March 13. | N/A | All Bureaus | 2020-03-11 | Complete
OFM e-mails bureaus the manual templates and the final version of the Financial Statements Guidance. | N/A | OFM | 2020-03-16 | Complete
All bureaus enter Improper Payments data into HFM. | K | Servicing Bureaus | 4/1/2020 - 4/10/2020
All bureaus load into HFM and verify Preclose ETBs and Preclose supplemental data submissions. All bureaus enter into HFM footnotes and DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 4/1/20 - 4/17/20
All bureaus canvass their program offices for all unasserted claims through Mar. 31. | F | All Bureaus | 2020-04-01 | Complete
All bureaus submit OFM Quarterly Bureau GAAP Compliance Questionnaire. (OFM will follow-up with bureaus, as needed.) | A | All Bureaus | 2020-04-02 | Complete
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events Questionnaire. (OFM will follow-up with bureaus, as needed.) | A | All Bureaus | 2020-04-02 | Complete
Treasury GTAS IGT Reporting Window 2nd Quarter | N/A |  | April 4, 2020 8 a.m. – April 16, 2020 2 p.m.
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: Dates reflect Treasury’s open window period. The actual date for bureaus to finalize and certify the TROR and submit to OFM is April 30, 2020. | A | All Bureaus | 4/14/20 - 4/30/20
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | NOAA, Census, USPTO, NTIS | 2020-04-07
Applicable bureaus submit to NIST the shared TAS balances. | N/A | Servicing Bureaus | 2020-04-07
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Agency Submission Form | C | All Bureaus | 2020-04-08
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR & TSR. Please submit to USPTO by noon on April 7 . (If information is available sooner, please do not wait until the deadline to submit to partner bureaus.) | B | Servicing Bureaus | 2020-04-08
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM copy of legal letter update through Mar 31. | F | OGC, OCR, USPTO | 2020-04-09 | Complete
All bureaus submit to OFM unasserted claims through Mar 31 per the Department’s materiality threshold. | F | Servicing Bureaus | 2020-04-09
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2020-04-10
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. All bureaus submit Intra-Commerce Checklist Part I to OFM. | B | Servicing Bureaus | 2020-04-13
All bureaus submit to OFM Preliminary Intragovernmental TDR for providing and receiving bureau transactions. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2020-04-10
Applicable bureaus submit to OFM confirmation of Distributed Offsetting Receipts for April (cumulative fiscal year-to-date). | N/A | Servicing Bureaus | 2020-04-13
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, and actual FECA costs. (If data is not received in time, bureaus will estimate or default to prior SEP 30 data.) (If data arrives before final financial statements preparation, OFM MAY adjust bureau data.) | N/A | OFM | 2020-04-13 | NLT
OFM submits to selected partner agencies Intragovernmental Providing and Receiving TDR and TSR. | C | OFM | 2020-04-13
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: Dates reflect Treasury’s open window period. The actual date for bureaus to finalize and certify the TROR and submit to OFM is April 30, 2020. | A | All Bureaus | 4/14/20 - 4/30/20
OFM will generate and send out a draft GTAS vs HFM reconciliation to the bureaus. The Draft Reconciliation should be used as a tool to help resolve GTAS vs HFM differences prior to the closure of the two windows. | N/A | Servicing Bureaus | 2020-04-14
OFM sends Distributed Offsetting Receipts for April (cumulative). | N/A | OFM | 2020-04-15
All bureaus submit Tie-points, SBR vs SF 132s comparison, Anomalies, F099 and F999 (Unidentified) difference explanations to OFM. | N/A | Servicing Bureaus | 2020-04-17
All bureaus submit International Agreements and Treaties Template to OFM. |  | All Bureaus | 2020-04-17
Stand-alone bureaus (applies to USPTO) submits stand-alone financial statements and footnotes. | A | USPTO | 2020-04-17
All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2020-04-20
OFM reviews bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2020-04-20
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-level Summaries. OFM specifically identifies the category differences requiring corrections by bureaus. | B | OFM | 2020-04-20
All bureaus submit Review Checklist Part I to OFM. | A | Servicing Bureaus | 2020-04-20
OFM will generate and send out the final GTAS vs HFM reconciliation to the bureaus. | N/A | Servicing Bureaus | 4/20/2020 (Noon)
Bureaus respond to OFM review comments and resolve any outstanding issues. | N/A | Servicing Bureaus | 2020-04-21
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2020-04-21
All bureaus submit to OFM explanations for significant financial statement fluctuations. Note: OFM may request additional explanations/information. | A | Servicing Bureaus | 2020-04-22
All bureaus submit Review Checklist Part II to OFM | A | Servicing Bureaus | 2020-04-23
OFM reviews bureaus’ fluctuation analysis and provides comments to bureaus. | N/A | OFM | 2020-04-23
Bureaus and OFM reconcile intragovernmental transactions with federal agencies. | C | OFM | 4/23/20 - 5/1/20
All bureaus submit to OFM the TROR (copy of actual submission), the TROR Certification, Verification, and Reconciliation, the TROR Transmittal Confirmation Report, and ALL variance explanations. | A | Servicing Bureaus | 2020-04-30 | TROR window is from 4/14 to 4/30.
All bureaus submit to OFM final, signed Review Checklists (complete), with bureau CFO Review Checklist, Part III, signed by bureau CFO and financial manager. Date subject to change upon release of Q2 DATA Act schedule from the DOC DATA Act team. | A | All Bureaus | 2020-05-15 | Data Act Cert due date is 5/15.

## FY20 Q3 (hidden)
Department of Commerce FYs 2019/2020 Financial Statements Guidance
FY 2019 Q3 Due Date Calendar
GTAS reporting window: 7/5/2019 - 7/18/2019
HFM reporting window: 7/1/2019 - 7/22/2019
Action | Attachment Reference | Responsible Party | Due Dates | Comments
OFM sends Quarterly Bureau Transactions/Significant Events and GAAP Questionnaires to bureaus. | A | OFM | 2019-06-03
OFM e-mails bureaus a summary of significant new requirements/changes to the FS process. | A | OFM | 2019-06-07
OFM e-mails bureaus the draft version of Financial Statements Guidance for bureau comment. | N/A | OFM | 2019-06-07
OFM e-mails bureaus the manual templates and the final version of the Financial Statements Guidance. | N/A | OFM | 2019-06-14
All bureaus canvass their program offices for all unasserted claims through June 30. | F | All Bureaus | 2019-07-01
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events Questionnaire. OFM will follow-up with bureaus, as needed. | A | All Bureaus | 2019-07-02
All bureaus submit GAAP Compliance Questionnaire. OFM will follow-up with bureaus, as needed. | A | Servicing Bureaus | 2019-07-02
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Agency Submission Form | C | All Bureaus | 2019-07-08
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | NOAA, Census, USPTO, NTIS | 2019-07-08
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR and TSR. * Please submit to USPTO by July 5. | B | NOAA, Census, NIST, NTIS | 2019-07-08
Applicable bureaus submit to NIST the SHARED TAS GTAS templates. * The Shared TAS data for DoC is reported in a consolidated file for GTAS. However, Shared TAS data for bureau balances must be submitted by bureau in Hyperion. | N/A | NOAA, Census, USPTO, NTIS | 2019-07-08 | Should be at least one day before GFA submission form data is due
All bureaus submit to OFM unasserted claims through June 30 per the Department’s materiality threshold. | F | All Bureaus | 2019-07-09
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM copy of legal letter update through June 30. | F | USPTO/OFM | 2019-07-09
All bureaus submit to OFM Preliminary Intragovernmental TDR. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 2019-07-10
OFM submits to selected partner agencies preliminary Intragovernmental Providing and Receiving TDR and TSR. | N/A | OFM | 2019-07-11
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. All bureaus submit Intra-Commerce Checklist Part I to OFM. *Please submit to USPTO by July 11. | B | Servicing Bureaus | 2019-07-11
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2019-07-12
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, and actual FECA costs. (If data is not received in time, bureaus will estimate or default to prior September 30 data.) (If data arrives before final financial statements preparation, OFM MIGHT adjust bureau data.) | N/A | OFM | 2019-07-12
OFM sends Distributed Offsetting Receipts for months of April - June for review. | N/A | OFM | 2019-07-15
All bureaus submit to OFM explanations for tie-point differences (including BP tie-points). Bureaus are asked to sue the BP Tie Point template for submitting explanations. | A | Servicing Bureaus | 2019-07-16
All bureaus submit to OFM explanations for SBR vs. SF132 comparison. Bureaus are asked to use the SBR vs SF 132 template for submitting explanations. | A | Servicing Bureaus | 2019-07-16
All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2019-07-16
All bureaus submit to OFM Review Checklists Part I signed by bureau Finance Manager (excluding Subsequent Review Checklist), with explanations for anomaly balances, net position analyses differences, and F999 (Unidentified) differences. Bureaus are asked to use the template for the Net Position Analyses explanations. | A | Servicing Bureaus | 2019-07-17
OFM reviews bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2019-07-17
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-Level Summaries for items requiring further analysis and/or corrective action. OFM specifically identifies the category differences requiring corrections by bureaus. | B | OFM | 2019-07-17
All bureaus submit to OFM explanations for all preliminary differences ($0 threshold) between HFM and GTAS. When applicable, an adjustment in GTAS or journal entry in HFM format will need to be submitted | N/A | Servicing Bureaus | 2019-07-17
USPTO submits stand-alone financial statements. | A | USPTO | 2019-07-18
Bureaus respond to OFM review comments and resolve any outstanding issues that may impact OFM’s LOCKDOWN of HFM ETB data, and the start of consolidated reporting. | N/A | All Bureaus as Needed | 2019-07-18
Applicable bureaus submit to OFM confirmation regarding Distributed Offsetting Receipts for months of April – June (Q3). | N/A | Servicing Bureaus | 2019-07-19
All bureaus submit to OFM explanations for significant financial statement and footnote fluctuations. | A | Servicing Bureaus | 2019-07-19
All bureaus submit to OFM: a) Manual footnotes data (Loans Receivable Prior Period Adjustments, Note 20, Note 21 NEW and Note 23), if applicable b) Manual footnotes text matrix c) Manual RSI (excluding intragovernmental schedules), if applicable d) Manual RSSI, if applicable | A | Servicing Bureaus | 2019-07-22
USPTO submits stand-alone footnotes | A | USPTO | 2019-07-22
OFM reviews bureaus’ statement fluctuation analyses and provides comments to bureaus. | A | Servicing Bureaus | 2019-07-22
All bureaus submit to OFM explanations for all final differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. | N/A | Servicing Bureaus | 2019-07-22
All bureaus submit to OFM signed Review Checklists (including Subsequent Review Checklist), with CFO Review Checklist Part II signed by bureau Finance Manager. | A | All Bureaus | 2019-07-23
All bureaus submit to OFM explanations for footnote fluctuations. | A | Servicing Bureaus | 2019-07-23
OFM reviews bureaus’ St of BR vs. SF 133s data/explanations and provides comments to bureaus. | N/A | Servicing Bureaus | 2019-07-23
OFM submits to Consolidated IPA and OIG Department’s Legal Letter Text. | N/A | OFM | 2019-07-24
OFM submits to Consolidated IPA Department’s OGC legal contingencies response for Quarter 3. | N/A | OFM | 2019-07-24
OFM reviews bureaus’ footnote fluctuation analyses and provides comments to bureaus | N/A | OFM | 2019-07-24
OFM submits to OMB Balance Sheet, St of Net Cost, SCNP. | N/A | OFM | 2019-07-30
All bureaus submit to OFM the TROR (copy of actual submission), the TROR Certification, Verification, and Reconciliation, the TROR Transmittal Confirmation Report. *Due Date matches Treasury deadlines | A | Servicing Bureaus | 2019-07-31
All bureaus submit to OFM final, signed Review Checklists (complete), with bureau CFO Review Checklist, Part III, signed by bureau CFO. | A | All Bureaus | 2019-08-09
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: Dates reflect Treasury’s open window period. The actual date for bureaus to finalize and certify the TROR and submit to OFM is July 31, 2019. | A | Servicing Bureaus | 7/16/2019 – 7/31/2019
All bureaus enter required footnote data into HFM. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. | K | Servicing Bureaus | July 1 – July 22, 2019
All bureaus enter Improper Payments data into HFM. | K | Servicing Bureaus | July 1, 2019 – July 12, 2019
All bureaus load into HFM and verify Preclose ETBs and Preclose supplemental data submissions. All bureaus enter into HFM \ DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | July 1, 2019 – July 16, 2019
All bureaus: a) Enter SF 133s data into HFM St of BR vs. SF 133s Schedule b) Submit to OFM explanations for St of BR vs. SF 133s differences c) Email to OFM complete SF 133s d) Submit to OFM any journal entries resulting from SF-133 vs. ETB differences. | A | Servicing Bureaus | July 15, 2019 – July 22, 2019
Bureaus and OFM reconcile intragovernmental transactions with federal agencies | C | OFM/Applicable Servicing Bureaus | July 24 – 31, 2019
Treasury GTAS ATB Reporting Window (Period 9) | N/A | Servicing Bureaus | July 5, 8 am – July 18, 2019, 2pm
Treasury GTAS IGT Reporting Window 3rd Quarter | N/A | Servicing Bureaus | July 5, 8 am – July 23, 5pm
OFM submits to OMB unaudited notes, RSI, RSSI, and OI and comparative significant variance analyses for the Balance Sheet, SNC, and SCNP. | A | OFM | No Later Than 45 business days after June 30
OFM submits to Consolidated IPA Department’s financial statements, footnotes, RSI, RSSI, consolidating financial statement supporting schedules, trial balances, and intra-Commerce TSRs. | N/A | OFM | Various Dates (Late July/Early August)

## FY20 Q4 (hidden)
Department of Commerce FYs 2019/2020 Financial Statements Guidance
FY 2019 Q4 Due Date Calendar
GTAS reporting window: 10/4/2019 - 10/17/2019
HFM reporting window: 10/1/2019 - 10/11/2019
Action | Attachment Reference | Responsible Party | Due Dates | Comments
OFM sends Quarterly Bureau Transactions/Events and GAAP Questionnaires to bureaus. | A | OFM | 2019-09-06 | Completed
OFM e-mails bureaus the DRAFT version of the Financial Statements Guidance for bureau comment. | N/A | OFM | 2019-09-09 | Completed
OFM e-mails bureaus a summary of significant new requirements/changes to the FS process. (PART I) | A | OFM | 2019-09-10 | Completed
OFM e-mails bureaus the manual templates and the FINAL version of the Financial Statements Guidance. | N/A | OFM | 2019-09-16 | Completed
All bureaus canvass their program offices for all unasserted claims through September 30. | F | All Bureaus | 2019-10-01 | Completed
All bureaus load into HFM and verify Preclose ETBs and PreClose supplemental data submissions. (HFM window is 10/1/2019 to 10/11/2019) All bureaus enter into HFM footnotes and DOL/OPM confirmation. All bureaus print/verify HFM data/reports during the window period. Unless requested by the bureaus, OFM will review/provide comments after the window close date. Updates to HFM for significant changes will be handled on a case-by-case basis. | K | Servicing Bureaus | 10/1/2019 - 10/11/2019
Bureaus submit GAAP Compliance Questionnaires. OFM will follow-up with bureaus, as needed. | A | Servicing Bureaus | 2019-10-02
All bureaus submit OFM Quarterly Bureau Transactions/Significant Events templates. OFM will follow-up with bureaus, as needed. | A | All Bureaus | 2019-10-02 | Completed
Bureaus submit Treaties and International Agreements Templates. OFM will follow-up with bureaus, as needed. All bureaus must complete and submit a template - see instructions in template for negative confirmations. | N/A | All Bureaus | 2019-10-02 | Completed
Applicable bureaus submit to NIST the DM/G&B trial balances. | N/A | NOAA, Census, USPTO, NTIS | 2019-10-04 | Completed
All bureaus submit to partner bureaus Preliminary Intra-Commerce TDR and TSR. * Please submit to USPTO by 10/4/2019. | B | Servicing Bureaus | 2019-10-07 | Completed
All bureaus submit answers to standard questions for individual improper payments $10,000 or greater. | K | Servicing Bureaus | 2019-10-07
All bureaus enter Improper Payments data into HFM from 10/1/2019 to 10/7/2019. | K | All Bureaus | 2019-10-07
All bureaus submit to OFM their Quarter-end balances with the General Fund of the U.S. Government, using the General Fund Agency Submission Form | C | All Bureaus | 2019-10-08 | Completed
Applicable bureaus submit to NIST the SHARED TAS GTAS templates. * The Shared TAS data for DoC is reported in a consolidated file for GTAS. However, Shared TAS data for bureau balances must be submitted by bureau in Hyperion. | N/A | NOAA, Census, USPTO, NTIS | 2019-10-08 | Should be at least one day before GFA submission form data is due
OFM provides bureaus with data for pensions and other retirement benefits, Treasury Judgment Fund payments, actual FECA costs, and Actuarial FECA Liability breakdown by bureau. (If data is not received in time, bureaus will estimate. If data arrives before final financial statements preparation, OFM may adjust bureau data.) | N/A | OFM | 2019-10-08 | Completed
All bureaus submit to OFM unasserted claims through September 30 per the Department’s materiality threshold. | F | Servicing Bureaus | 2019-10-09 | *Date changed to 10/9 to match legal letter.
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM a copy of initial legal letter response as of September 30. | F | OGC/OFM | 2019-10-09 | *Date changed to 10/9 to match legal letter.
All bureaus submit to OFM Preliminary Intragovernmental TDR for providing and receiving bureau transactions. Note: Negative response is needed for “no transactions.” | C | Servicing Bureaus | 10/10/2019 (Noon) |  | *needs to be earlier in FY 2020 - other agencies are providing us data much sooner.
All bureaus submit to partner bureaus Reconciled Intra-Commerce TDR and TSR. All bureaus submit Intra-Commerce Checklist Part I to OFM. | B | Servicing Bureaus | 10/9/2019 (Noon)
OFM sends Distributed Offsetting Receipts for months of July - September for review. | N/A | OFM | 2019-10-10
All bureaus submit to OFM: a) Manual footnotes text matrix b) Explanations for tie-point differences, including BP tie-points, and SBR vs SF 132s comparison, if applicable. Bureaus are asked to use the new BP Tie point and SBR vs SF 132 for submitting explanations. c) Manual footnotes data (Loans Receivable Prior Period Adjustments, Note 20, Note 21 NEW and Note 23, Prior Period Adjustment), if applicable d) Manual RSI (excluding intragovernmental schedules), if applicable e) Manual RSSI, if applicable. | A | Servicing Bureaus | 2019-10-11
All bureaus submit to OFM Intra-governmental TDR for providing and receiving bureau transactions and Intragovernmental Checklist Part I. | C | Servicing Bureaus | 2019-10-11
All bureaus submit explanations for anomaly balances, net position analyses differences, and F999 (Unidentified). | A | Servicing Bureaus | 2019-10-11
OFM sends to bureaus preliminary GTAS v HFM Analysis. | N/A | OFM | 2019-10-12 | *Saturday/Monday
OFM reviews Bureaus’ data/reports and provides comments to bureaus. | N/A | OFM | 2019-10-12 | *Saturday
All bureaus submit Review Checklist Part I to OFM signed by bureau Finance Manager (excluding Subsequent Review Checklist). | A | All Bureaus | 2019-10-11
OFM prepares and sends to bureaus Intra-Commerce Transaction Grids and High-level Summaries. OFM specifically identifies the category differences requiring corrections by bureaus. | B | OFM | 2019-10-12 | *Saturday
All bureaus submit explanations for significant financial statement and footnote fluctuations to OFM. | A | Servicing Bureaus | 2019-10-15
Bureaus respond to OFM review comments, and resolve any outstanding issues that may impact OFM’s LOCKDOWN of HFM ETB data, and the start of consolidated reporting. | N/A | All Bureaus (as needed) | 10/15/2019 (Noon)
Applicable bureaus submit to OFM confirmation regarding Distributed Offsetting Receipts for month of July - September | N/A | Servicing Bureaus | 2019-10-15
USPTO submits stand-alone financial statements and footnotes. | A | USPTO | 2019-10-15
OFM reviews bureaus’ fluctuation analyses and provides comments to bureaus. | N/A | OFM | 10/16/2019 (Noon)
All bureaus submit CFO Review Checklist Part II to OFM, signed by bureau Finance Manager. | A | All Bureaus | 2019-10-17
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. (For Preliminary Analysis) | N/A | Servicing Bureaus | 10/15/2019 (Noon)
OFM sends to bureaus final GTAS vs. HFM Analysis | N/A | OFM | 2019-10-18
OFM submits to Consolidated IPA Department’s first draft financial statements, footnotes, RSI, RSSI, consolidating financial statement supporting schedules, trial balances, and final intra-Commerce TSRs. | N/A | OFM | 2019-10-18
OFM submits to Consolidated IPA Department’s Legal contingencies Matrix (and Patty McBarnette) as of September 30. | N/A | OFM | 2019-10-18
OFM submits to Consolidated IPA listing of contingent liabilities as of September 30. | N/A | OFM | 2019-10-18
All bureaus submit to OFM explanations for all differences ($0 threshold) between HFM and GTAS. When applicable, a journal entry in HFM format will need to be submitted. (For Final Analysis) | N/A | OFM | 2019-10-21
All bureaus submit to partner bureaus Audit Adjusted Intra-Commerce TDR and TSR, and submit to OFM Intra-Commerce Checklist Part II. | B | All Bureaus | 2019-10-21
All bureaus: a) Enter SF 133s data into HFM St of BR vs. SF 133s Schedule b) Submit to OFM explanations/comments for SF 133s vs. St of BR analysis c) Email to OFM complete SF 133s (Also, include the overall summary at the bureau level). Date range: 10/18/2019 to 10/22/2019 | A | Servicing Bureaus | 2019-10-22
OFM reviews bureaus’ St of BR vs. SF 133s data/explanations and provides comments to bureaus. | N/A | OFM | 2019-10-23
All bureaus submit to OFM Audit Adjusted Intra-governmental TDR for providing and receiving bureau transactions, and Intra-governmental Checklist Part II. | C | All Bureaus | 2019-10-25
All bureaus canvass their program offices for all unasserted claims through October 31. | F | All Bureaus | 2019-11-01 | No Longer Required
All bureaus submit to OFM unasserted claims through October 31 per the Department’s materiality threshold. | F | All Bureaus | 2019-11-01 | No Longer Required
Department’s OGC, Department’s OCR, and USPTO’s Solicitor’s Office submit to OFM a copy of the updated legal letter response as of October 31. | F | OGC/OFM | 2019-11-01
All bureaus e-mail to OFM updates to Improper payments data. | K | Servicing Bureaus | 2019-11-04
OFM submits to Consolidated IPA Department’s final financial statements, footnotes, RSI, RSSI, consolidating financial statement schedules, trial balances | N/A | OFM | 2019-11-04
All bureaus submit to OFM the final, signed Review Checklists (complete), with bureau CFO Review Checklist, Part III, signed by bureau CFO. | A | All Bureaus | 2019-11-06
Department’s CFO submits to Consolidated IPA Department's final Agency Financial Report. | N/A | OFM | 2019-11-07
USPTO submits to OFM unasserted claims through November 8 (noon) for the Department’s materiality threshold. | F | USPTO | 2019-11-08 | Only USPTO
Consolidated IPA provides OFM with draft summary of material weaknesses, significant deficiencies, and compliance matters. | N/A | KPMG | 2019-11-13
All bureaus (except USPTO) submit to OFM unasserted claims through November 14 (noon) per the Department’s materiality threshold. | F | All Bureaus (Except USPTO) | 2019-11-14
USPTO submits to OFM unasserted claims through November 15 (noon) per the Department’s materiality threshold. | F | USPTO | 2019-11-15
All bureaus submit to Treasury the Treasury Report on Receivables (TROR). NOTE: The Treasury window period ends Nov 15, 2019; however, bureaus’ window period needs to be accelerated to allow for OFM review of bureaus’ TROR data and to allow year-end reporting requirements. Due to year-end reporting requirements, the actual date for bureaus to finalize and certify the TROR and submit to OFM has been accelerated to 10/31/2019. | A | Servicing Bureaus | 2019-10-31